## Milestone Months
Country / Budget | Milestone | Valid months | First month | Last month | # months | Type | Title | Confidence | Notes / conflicts | Source
Botswana | BOT01 | Oct-26 to Dec-26 | Oct-26 | Dec-26 | 3 | Milestone | Implementation governance & transition baseline | High |  | AFGHSP_Botswana_Workplan_Milestone_Level.xlsx > tab 7 'Implementation Timeline' (Gantt)
Botswana | BOT02 | Oct-26 to Dec-26 | Oct-26 | Dec-26 | 3 | Milestone | DCHIS dashboard-driven review cycles | High |  | AFGHSP_Botswana_Workplan_Milestone_Level.xlsx > tab 7 'Implementation Timeline' (Gantt)
Botswana | BOT03 | Oct-26 to Nov-26 | Oct-26 | Nov-26 | 2 | Milestone | Secure device management, cybersecurity & data protection | High |  | AFGHSP_Botswana_Workplan_Milestone_Level.xlsx > tab 7 'Implementation Timeline' (Gantt)
Botswana | BOT04 | Oct-26 to Dec-26 | Oct-26 | Dec-26 | 3 | Milestone | eLMIS requirements & priority interoperability flows | High |  | AFGHSP_Botswana_Workplan_Milestone_Level.xlsx > tab 7 'Implementation Timeline' (Gantt)
Botswana | BOT05 | Oct-26 to Dec-26 | Oct-26 | Dec-26 | 3 | Milestone | Commodity quantification & stock visibility | High |  | AFGHSP_Botswana_Workplan_Milestone_Level.xlsx > tab 7 'Implementation Timeline' (Gantt)
Botswana | BOT06 | Oct-26 to Dec-26 | Oct-26 | Dec-26 | 3 | Milestone | eIDSR integration & client portal services | High |  | AFGHSP_Botswana_Workplan_Milestone_Level.xlsx > tab 7 'Implementation Timeline' (Gantt)
Botswana | MBOT00 | Sep-26 to Sep-26 | Sep-26 | Sep-26 | 1 | Milestone | Mobilization & operational readiness | High |  | AFGHSP_Botswana_Workplan_Milestone_Level.xlsx > tab 7 'Implementation Timeline' (Gantt)
Burundi | BUR01 | Sep-26 to Dec-26 | Sep-26 | Dec-26 | 4 | Milestone | Priority-district outbreak alerts notified within one day | High |  | AFGHSP_Burundi_Workplan_Milestone_Level.xlsx > tab 7 'Implementation Timeline' (Gantt)
Burundi | BUR02 | Oct-26 to Feb-27 | Oct-26 | Feb-27 | 5 | Milestone | Data-review coaching delivered; end-line DQA shows improvement | High |  | AFGHSP_Burundi_Workplan_Milestone_Level.xlsx > tab 7 'Implementation Timeline' (Gantt)
Burundi | BUR03 | Oct-26 to Feb-27 | Oct-26 | Feb-27 | 5 | Milestone | Harmonized DHIS2/EMR tools & malaria module operational | High |  | AFGHSP_Burundi_Workplan_Milestone_Level.xlsx > tab 7 'Implementation Timeline' (Gantt)
Burundi | BUR04 | Sep-26 to Feb-27 | Sep-26 | Feb-27 | 6 | Milestone | Digital decision-support tools used for program & outbreak decisions | High |  | AFGHSP_Burundi_Workplan_Milestone_Level.xlsx > tab 7 'Implementation Timeline' (Gantt)
Burundi | BUR05 | Sep-26 to Feb-27 | Sep-26 | Feb-27 | 6 | Milestone | National HIS resilience, support & MoH operational ownership | High |  | AFGHSP_Burundi_Workplan_Milestone_Level.xlsx > tab 7 'Implementation Timeline' (Gantt)
Burundi | BUR06 | Sep-26 to Feb-27 | Sep-26 | Feb-27 | 6 | Milestone | Priority interoperability exchanges validated & operational | High |  | AFGHSP_Burundi_Workplan_Milestone_Level.xlsx > tab 7 'Implementation Timeline' (Gantt)
Burundi | BUR07 | Sep-26 to Feb-27 | Sep-26 | Feb-27 | 6 | Milestone | Lab-to-EOC/surveillance bridge operational | High |  | AFGHSP_Burundi_Workplan_Milestone_Level.xlsx > tab 7 'Implementation Timeline' (Gantt)
Burundi | BUR08 | Sep-26 to Mar-27 | Sep-26 | Mar-27 | 7 | Milestone | Digital-health TWGs operate with mandates, action closure & MoH planning | High |  | AFGHSP_Burundi_Workplan_Milestone_Level.xlsx > tab 7 'Implementation Timeline' (Gantt)
Burundi | MBUR0 | Sep-26 to Dec-26 | Sep-26 | Dec-26 | 4 | Mobilization (not in budget) | Mobilization & Operational Readiness | High |  | AFGHSP_Burundi_Workplan_Milestone_Level.xlsx > tab 7 'Implementation Timeline' (Gantt)
CORE G2G | MM0.3 | Sep-26 to Dec-26 | Sep-26 | Dec-26 | 4 | Mobilization (not in budget) | Mobilization & operational readiness (PFM & G2G) | High |  | G2G doc: milestone header + activity table (Sep-Dec 2026)
CORE G2G | T1.5 | Sep-26 to Sep-27 | Sep-26 | Sep-27 | 13 | Milestone | G2G milestone frameworks, training & learning | Medium | Header 'Start/End' and Planned Milestone Date say Aug-2027, and the Gantt title says 'FY2027 (Sep 2026 to Aug 2027)', but 5 activities (A1, A12-A15) and the Gantt run to Sep-2027. Followed activity-level evidence; if Aug-27 is right, drop Sep-27. | G2G doc: activity table + Gantt (T1.5-A1..A15)
CORE-EMR ECHIS | C2 | Oct-26 to Sep-27 | Oct-26 | Sep-27 | 12 | Milestone | eCHIS global public good | Medium | Doc never states what calendar month 'Month 1' is. Month 1 = Oct-26 is inferred: Q3 reviews at M7-M9 (Apr-Jun) and the T1.8/C2 planned milestone date of 14 Sep 2027 only fit Oct-26 start. | EMR/C2/T1.8 doc: 'Period Month 1-Month 12' + activity table + Gantt agree (M1-M12)
CORE-EMR ECHIS | MM0.1 | Sep-26 to Dec-26 | Sep-26 | Dec-26 | 4 | Mobilization (not in budget) | Mobilization & operational readiness (C2) | High |  | EMR/C2/T1.8 doc: header + activity table (Sep-Dec 2026)
CORE-EMR ECHIS | MM0.2 | Sep-26 to Dec-26 | Sep-26 | Dec-26 | 4 | Mobilization (not in budget) | Mobilization & operational readiness (T1.8) | High |  | EMR/C2/T1.8 doc: header + activity table (Sep-Dec 2026)
CORE-EMR ECHIS | T1.8 | Oct-26 to Sep-27 | Oct-26 | Sep-27 | 12 | Milestone | High-impact HIV interventions (Kenya, Eswatini) | Medium | Same Month 1 = Oct-26 inference as C2. Minor: T1.8-A05 table says M1-M2, Gantt shows M2 only. | EMR/C2/T1.8 doc: 'Period Month 1-Month 12' + activity table + Gantt agree (M1-M12)
CORE-Ebola | E1 | Jan-27 to Jun-27 | Jan-27 | Jun-27 | 6 | Milestone | EVD preparedness, early warning, surge staffing & contact tracing | Medium | CONFLICT: milestone header End Month and Planned Milestone Date say Sep-2027 (Q4 FY2027), and the summary Gantt shades Jan-Sep, but every activity ends by Jun-27 and all E1 evidence is due Q3 FY2027. Window shown = activity window; extend to Sep-27 if the header governs. | DRC/EVD doc: activity table + detailed Gantt agree (Jan-Jun 2027); evidence due Q3 FY2027
CORE-Ebola | E2 | Jan-27 to Sep-27 | Jan-27 | Sep-27 | 9 | Milestone | Cross-border EVD detection & response coordination | Medium | CONFLICT: milestone header Start Month says October 2026, but the first activity (E2-A1.1) starts Jan-27 in the table and both Gantts. Followed the activities. | DRC/EVD doc: activity table + detailed Gantt + summary Gantt agree (Jan-Sep 2027)
CORE-Ebola | E3 | Oct-26 to Sep-27 | Oct-26 | Sep-27 | 12 | Milestone | EVD laboratory connectivity & case-management data readiness | Medium | SUMMARY GANTT DISAGREES: it shades E3 Jan-Sep 2027 like the other EVD milestones; the header, the activity table (E3-A1 starts M1) and the detailed Gantt all start Oct-26. | DRC/EVD doc: header (Month 1-12) + activity table + detailed Gantt agree
CORE-Ebola | MM0.6 | Oct-26 to Dec-26 | Oct-26 | Dec-26 | 3 | Mobilization (not in budget) | Mobilization & operational readiness (Ebola/DRC) | High |  | DRC/EVD doc: header (Oct-Dec 2026) + activity table + both Gantts agree
CORE-Ebola | T1.4 | Jan-27 to Sep-27 | Jan-27 | Sep-27 | 9 | Milestone | Faster EVD detection, notification & response (7-1-7) | High |  | DRC/EVD doc: header + activity table + both Gantts agree
CORE-HIC | C1a | Sep-26 to Mar-27 | Sep-26 | Mar-27 | 7 | Milestone | Generalized HIC Digital Kit (global good) | Medium | GANTT DISAGREES: the C1a bars are compressed into Sep-Dec 2026 (e.g. A12 publication shown Dec-26 vs Mar-27 in the table; A4-A11 start/end 1-2 months early), plus a Jan-Aug 2027 'kit maintenance' row (A13) that has no activity-table row (the text assigns maintenance to C1b). Followed the activity table. Header start is Oct-26; A1-A3 begin Sep-26. | HIC doc: activity table (Sep-26..Mar-27); header says Month 1 (Oct-26)..Month 6 (Mar-27); Planned Milestone Date 31 Mar 2027
CORE-HIC | C1b | Sep-26 to Aug-27 | Sep-26 | Aug-27 | 12 | Milestone | HIC country implementations (Kenya, Botswana, Sierra Leone) | Medium | Header says Month 1 (Oct-26)..Month 11 (Aug-27) while the progress-review table lists 'Final Achievement' at Month 12 (Sep-27); A1 starts Sep-26. Gantt row A11 has a Jul-27 gap (Jun and Aug only) vs. table Jun-Aug. Table lists activity 'C1b-A17' (likely A7). | HIC doc: activity table + Gantt agree (Sep-26..Aug-27)
CORE-HIC | MM0.5 | Sep-26 to Dec-26 | Sep-26 | Dec-26 | 4 | Mobilization (not in budget) | Mobilization & operational readiness (HIC) | High | No bar for MM0.5 in the doc's Gantt. | HIC doc: milestone header + activity table (Sep-Dec 2026)
CORE-Supply Chain | C5 | Oct-26 to Sep-27 | Oct-26 | Sep-27 | 12 | Milestone | Supply Chain Control Tower | High | Header describes build as Month 1-9 (to Jun-27) with sustainment/handover to Month 12; window shown includes sustainment. | Supply Chain doc: activity table + Gantt agree (A1-A12)
CORE-Supply Chain | C6 | Oct-26 to Sep-27 | Oct-26 | Sep-27 | 12 | Milestone | eLMIS & last-mile supply chain digitization | High |  | Supply Chain doc: header + activity table + Gantt agree
CORE-Supply Chain | C7 | Oct-26 to Sep-27 | Oct-26 | Sep-27 | 12 | Milestone | Molecular Diagnostics Control Tower | High |  | Supply Chain doc: header + activity table + Gantt agree
CORE-Supply Chain | MM0.4 | Sep-26 to Dec-26 | Sep-26 | Dec-26 | 4 | Mobilization (not in budget) | Mobilization & operational readiness (Supply chain) | High | No bar for MM0.4 in the doc's Gantt. | Supply Chain doc: milestone header + activity table (Sep-Dec 2026)
CORE-Supply Chain | T1.6 | Oct-26 to Sep-27 | Oct-26 | Sep-27 | 12 | Milestone | Digitally enabled diagnostics-to-treatment linkage | High |  | Supply Chain doc: header (Month 1-12) + activity table + Gantt agree
DRC | DRC00 | Oct-26 to Dec-26 | Oct-26 | Dec-26 | 3 | Mobilization (not in budget) | Mobilization | Medium | Gantt-only: the doc has no activity table or header dates for DRC00-DRC09 to cross-check. Payment-quarter target Q1 FY2027. | DRC/EVD doc: 'DRC AFGHS-P Foundation' rows of the summary and detailed Gantts (they agree)
DRC | DRC01 | Oct-26 to Feb-27 | Oct-26 | Feb-27 | 5 | Milestone | Cybersecurity | Medium | Gantt-only: the doc has no activity table or header dates for DRC00-DRC09 to cross-check. Payment-quarter target Q2 FY2027. | DRC/EVD doc: 'DRC AFGHS-P Foundation' rows of the summary and detailed Gantts (they agree)
DRC | DRC02 | Oct-26 to Mar-27 | Oct-26 | Mar-27 | 6 | Milestone | DHIS2 Polio/AFP | Medium | Gantt-only: the doc has no activity table or header dates for DRC00-DRC09 to cross-check. Payment-quarter target Q3 FY2027. | DRC/EVD doc: 'DRC AFGHS-P Foundation' rows of the summary and detailed Gantts (they agree)
DRC | DRC03 | Oct-26 to Mar-27 | Oct-26 | Mar-27 | 6 | Milestone | Data-quality supervision | Medium | Gantt-only: the doc has no activity table or header dates for DRC00-DRC09 to cross-check. Payment-quarter target Q3 FY2027. | DRC/EVD doc: 'DRC AFGHS-P Foundation' rows of the summary and detailed Gantts (they agree)
DRC | DRC04 | Oct-26 to Sep-27 | Oct-26 | Sep-27 | 12 | Milestone | Interoperability / eLIS | Medium | Gantt-only: the doc has no activity table or header dates for DRC00-DRC09 to cross-check. Payment-quarter target Q4 FY2027. | DRC/EVD doc: 'DRC AFGHS-P Foundation' rows of the summary and detailed Gantts (they agree)
DRC | DRC05 | Oct-26 to Sep-27 | Oct-26 | Sep-27 | 12 | Milestone | EMR site readiness | Medium | Gantt-only: the doc has no activity table or header dates for DRC00-DRC09 to cross-check. Payment-quarter target Q4 FY2027. | DRC/EVD doc: 'DRC AFGHS-P Foundation' rows of the summary and detailed Gantts (they agree)
DRC | DRC06 | Oct-26 to Sep-27 | Oct-26 | Sep-27 | 12 | Milestone | OpenMRS deployment | Medium | Gantt-only: the doc has no activity table or header dates for DRC00-DRC09 to cross-check. Payment-quarter target Q4 FY2027. | DRC/EVD doc: 'DRC AFGHS-P Foundation' rows of the summary and detailed Gantts (they agree)
DRC | DRC07 | Oct-26 to Sep-27 | Oct-26 | Sep-27 | 12 | Milestone | Data warehouse | Medium | Gantt-only: the doc has no activity table or header dates for DRC00-DRC09 to cross-check. Payment-quarter target Q4 FY2027. | DRC/EVD doc: 'DRC AFGHS-P Foundation' rows of the summary and detailed Gantts (they agree)
DRC | DRC08 | Oct-26 to Sep-27 | Oct-26 | Sep-27 | 12 | Milestone | DQR cycles | Medium | Gantt-only: the doc has no activity table or header dates for DRC00-DRC09 to cross-check. Payment-quarter target Q4 FY2027. | DRC/EVD doc: 'DRC AFGHS-P Foundation' rows of the summary and detailed Gantts (they agree)
DRC | DRC09 | Oct-26 to Sep-27 | Oct-26 | Sep-27 | 12 | Milestone | Digital governance | Medium | Gantt-only: the doc has no activity table or header dates for DRC00-DRC09 to cross-check. Payment-quarter target Q4 FY2027. | DRC/EVD doc: 'DRC AFGHS-P Foundation' rows of the summary and detailed Gantts (they agree)
El Salvador | ELS01 | Oct-26 to Apr-27 | Oct-26 | Apr-27 | 7 | Milestone | National Surveillance Dashboards & Outbreak-Intelligence Data Flows Operational | High |  | AFGHSP_El_Salvador_Workplan_Revised_Template.xlsx > tab 3 'Implementation Timeline' (Gantt)
El Salvador | ELS02 | Oct-26 to Apr-27 | Oct-26 | Apr-27 | 7 | Milestone | Alert escalation and response workflow achieves measurable notification and response timeliness in 25 sentinel health facilities | High |  | AFGHSP_El_Salvador_Workplan_Revised_Template.xlsx > tab 3 'Implementation Timeline' (Gantt)
El Salvador | ELS03 | Oct-26 to Apr-27 | Oct-26 | Apr-27 | 7 | Milestone | At least two cross-subsector interoperability use cases validated and used end-to-end | High |  | AFGHSP_El_Salvador_Workplan_Revised_Template.xlsx > tab 3 'Implementation Timeline' (Gantt)
El Salvador | ELS04 | Oct-26 to Apr-27 | Oct-26 | Apr-27 | 7 | Milestone | SUMEVE data quality assessment process implemented, institutionalized, and demonstrates measurable improvement in priority data quality | High |  | AFGHSP_El_Salvador_Workplan_Revised_Template.xlsx > tab 3 'Implementation Timeline' (Gantt)
El Salvador | ELS05 | Oct-26 to Apr-27 | Oct-26 | Apr-27 | 7 | Milestone | A phased community–PHC–referral cohort reports reliably and closes referral feedback loops | High |  | AFGHSP_El_Salvador_Workplan_Revised_Template.xlsx > tab 3 'Implementation Timeline' (Gantt)
El Salvador | MELS0 | Oct-26 to Nov-26 | Oct-26 | Nov-26 | 2 | Mobilization (not in budget) | Mobilization & Operational Readiness | High |  | AFGHSP_El_Salvador_Workplan_Revised_Template.xlsx > tab 3 'Implementation Timeline' (Gantt)
Eswatini | ESW01 | Oct-26 to Dec-26 | Oct-26 | Dec-26 | 3 | Milestone | National Data Center decision framework and implementation roadmap endorsed | High |  | AFGHSP_Eswatini_Workplan_V2.xlsx > tab 3 'Implementation Timeline' (Gantt)
Eswatini | ESW02 | Oct-26 to Dec-26 | Oct-26 | Dec-26 | 3 | Milestone | National HIE & Priority Clinical, Surveillance and Supply-Chain Integrations Operational | High |  | AFGHSP_Eswatini_Workplan_V2.xlsx > tab 3 'Implementation Timeline' (Gantt)
Eswatini | ESW03 | Oct-26 to Dec-26 | Oct-26 | Dec-26 | 3 | Milestone | Comprehensive CMIS Deployment to Four Additional and Four Inpatient Sites | High |  | AFGHSP_Eswatini_Workplan_V2.xlsx > tab 3 'Implementation Timeline' (Gantt)
Eswatini | ESW04 | Oct-26 to Dec-26 | Oct-26 | Dec-26 | 3 | Milestone | CMIS reliability/Helpdesk performance and DR/cybersecurity governance verified as separate payable sub-results | High |  | AFGHSP_Eswatini_Workplan_V2.xlsx > tab 3 'Implementation Timeline' (Gantt)
Eswatini | ESW05 | Oct-26 to Dec-26 | Oct-26 | Dec-26 | 3 | Milestone | CMIS Transition, Sustainability & Workforce Ownership Package | High |  | AFGHSP_Eswatini_Workplan_V2.xlsx > tab 3 'Implementation Timeline' (Gantt)
Eswatini | ESW06 | Oct-26 to Dec-26 | Oct-26 | Dec-26 | 3 | Milestone | CMIS programme enhancements and AI-enabled follow-up use cases operational | High |  | AFGHSP_Eswatini_Workplan_V2.xlsx > tab 3 'Implementation Timeline' (Gantt)
Eswatini | ESW07 | Oct-26 to Dec-26 | Oct-26 | Dec-26 | 3 | Milestone | Phase 1 MOU indicators mapped and available through reliable NDR pipelines and dashboards, with automated CMIS data management processes and optimized data pipelines | High |  | AFGHSP_Eswatini_Workplan_V2.xlsx > tab 3 'Implementation Timeline' (Gantt)
Eswatini | ESW08 | Oct-26 to Dec-26 | Oct-26 | Dec-26 | 3 | Milestone | Facility Data-Use Improvement & MOH Information Products Institutionalized | High |  | AFGHSP_Eswatini_Workplan_V2.xlsx > tab 3 'Implementation Timeline' (Gantt)
Eswatini | MESW0 | Oct-26 to Nov-26 | Oct-26 | Nov-26 | 2 | Mobilization (not in budget) | Mobilization & Operational Readiness | High |  | AFGHSP_Eswatini_Workplan_V2.xlsx > tab 3 'Implementation Timeline' (Gantt)
Ethiopia | ETH01 | Sep-26 to Feb-27 | Sep-26 | Feb-27 | 6 | Milestone | Dagu Platforms Operational and Interoperable | Medium | ASSUMED: no calendar anchor in file; Sep-26 assumed (same template family / Sept 21 2026 start) | AFGHSP_Ethiopia_ DOS Workplan Template.xlsx > tab 6 'Implementation Timeline' (Gantt)
Ethiopia | ETH02 | Sep-26 to Feb-27 | Sep-26 | Feb-27 | 6 | Milestone | Validated Indicators and Reporting Performance Improved | Medium | ASSUMED: no calendar anchor in file; Sep-26 assumed (same template family / Sept 21 2026 start) | AFGHSP_Ethiopia_ DOS Workplan Template.xlsx > tab 6 'Implementation Timeline' (Gantt)
Ethiopia | ETH03 | Sep-26 to Feb-27 | Sep-26 | Feb-27 | 6 | Milestone | Infrastructure Readiness in 48 Priority Facilities | Medium | ASSUMED: no calendar anchor in file; Sep-26 assumed (same template family / Sept 21 2026 start) | AFGHSP_Ethiopia_ DOS Workplan Template.xlsx > tab 6 'Implementation Timeline' (Gantt)
Ethiopia | ETH04 | Sep-26 to Feb-27 | Sep-26 | Feb-27 | 6 | Milestone | HRT and Health Financing Dashboards in Routine Use | Medium | ASSUMED: no calendar anchor in file; Sep-26 assumed (same template family / Sept 21 2026 start) | AFGHSP_Ethiopia_ DOS Workplan Template.xlsx > tab 6 'Implementation Timeline' (Gantt)
Ethiopia | ETH05 | Oct-26 to Mar-27 | Oct-26 | Mar-27 | 6 | Milestone | Analytics Platforms and Performance Dashboards Operational | Medium | ASSUMED: no calendar anchor in file; Sep-26 assumed (same template family / Sept 21 2026 start) | AFGHSP_Ethiopia_ DOS Workplan Template.xlsx > tab 6 'Implementation Timeline' (Gantt)
Ethiopia | ETH06 | Oct-26 to Mar-27 | Oct-26 | Mar-27 | 6 | Milestone | Priority Systems Exchanging Data Through Interoperability Services | Medium | ASSUMED: no calendar anchor in file; Sep-26 assumed (same template family / Sept 21 2026 start) | AFGHSP_Ethiopia_ DOS Workplan Template.xlsx > tab 6 'Implementation Timeline' (Gantt)
Ethiopia | ETH07 | Oct-26 to May-27 | Oct-26 | May-27 | 8 | Milestone | Multi-tenant EthioEMR Operational in 48 Facilities | Medium | ASSUMED: no calendar anchor in file; Sep-26 assumed (same template family / Sept 21 2026 start) | AFGHSP_Ethiopia_ DOS Workplan Template.xlsx > tab 6 'Implementation Timeline' (Gantt)
Ethiopia | ETH08 | Nov-26 to May-27 | Nov-26 | May-27 | 7 | Milestone | Provider Payment and CBHI Reform Package Piloted | Medium | ASSUMED: no calendar anchor in file; Sep-26 assumed (same template family / Sept 21 2026 start) | AFGHSP_Ethiopia_ DOS Workplan Template.xlsx > tab 6 'Implementation Timeline' (Gantt)
Ethiopia | ETH09 | Nov-26 to Aug-27 | Nov-26 | Aug-27 | 10 | Milestone | Regional Data Quality and Performance Review Improved | Medium | ASSUMED: no calendar anchor in file; Sep-26 assumed (same template family / Sept 21 2026 start) | AFGHSP_Ethiopia_ DOS Workplan Template.xlsx > tab 6 'Implementation Timeline' (Gantt)
Ethiopia | ETH10 | Sep-26 to Feb-27 | Sep-26 | Feb-27 | 6 | Milestone | HIV Case-Based Surveillance Dashboards Operational | Medium | ASSUMED: no calendar anchor in file; Sep-26 assumed (same template family / Sept 21 2026 start) | AFGHSP_Ethiopia_ DOS Workplan Template.xlsx > tab 6 'Implementation Timeline' (Gantt)
Ethiopia | ETH11 | Dec-26 to Jun-27 | Dec-26 | Jun-27 | 7 | Milestone | Urban eCHIS Modules Piloted and Ready for Scale-up | Medium | ASSUMED: no calendar anchor in file; Sep-26 assumed (same template family / Sept 21 2026 start) | AFGHSP_Ethiopia_ DOS Workplan Template.xlsx > tab 6 'Implementation Timeline' (Gantt)
Ethiopia | ETH12 | Dec-26 to Jun-27 | Dec-26 | Jun-27 | 7 | Milestone | Digital Governance, Cybersecurity and Platform Sustainability | Medium | ASSUMED: no calendar anchor in file; Sep-26 assumed (same template family / Sept 21 2026 start) | AFGHSP_Ethiopia_ DOS Workplan Template.xlsx > tab 6 'Implementation Timeline' (Gantt)
Ethiopia | ETH13 | Dec-26 to Jun-27 | Dec-26 | Jun-27 | 7 | Milestone | Integrated Surveillance and Response Systems Operational in Four Regions | Medium | ASSUMED: no calendar anchor in file; Sep-26 assumed (same template family / Sept 21 2026 start) | AFGHSP_Ethiopia_ DOS Workplan Template.xlsx > tab 6 'Implementation Timeline' (Gantt)
Ethiopia | ETH14 | Jan-27 to Aug-27 | Jan-27 | Aug-27 | 8 | Milestone | Health Financing Management, Claims Auditing and Oversight Strengthened | Medium | ASSUMED: no calendar anchor in file; Sep-26 assumed (same template family / Sept 21 2026 start) | AFGHSP_Ethiopia_ DOS Workplan Template.xlsx > tab 6 'Implementation Timeline' (Gantt)
Ethiopia | METH0 | Sep-26 to Oct-26 | Sep-26 | Oct-26 | 2 | Mobilization (not in budget) | Mobilization & Operational Readiness | Medium | ASSUMED: no calendar anchor in file; Sep-26 assumed (same template family / Sept 21 2026 start) | AFGHSP_Ethiopia_ DOS Workplan Template.xlsx > tab 6 'Implementation Timeline' (Gantt)
Kenya | KEN01 | Sep-26 to Dec-26 | Sep-26 | Dec-26 | 4 | Milestone | Integrated digital health and commodity-data workflows validated | High |  | AFGHSP_Kenya_DOS Workplan Template.xlsx > tab 7 'Implementation Timeline' (Gantt)
Kenya | KEN02 | Oct-26 to Dec-26 | Oct-26 | Dec-26 | 3 | Milestone | National data platforms, analytics and decision-use operational | High |  | AFGHSP_Kenya_DOS Workplan Template.xlsx > tab 7 'Implementation Timeline' (Gantt)
Kenya | KEN03 | Sep-26 to Dec-26 | Sep-26 | Dec-26 | 4 | Milestone | Malaria data quality and surveillance analytics validated | High |  | AFGHSP_Kenya_DOS Workplan Template.xlsx > tab 7 'Implementation Timeline' (Gantt)
Kenya | KEN04 | Sep-26 to Dec-26 | Sep-26 | Dec-26 | 4 | Milestone | Epidemic intelligence and alert proof of concept demonstrated | High |  | AFGHSP_Kenya_DOS Workplan Template.xlsx > tab 7 'Implementation Timeline' (Gantt)
Kenya | KEN05 | Sep-26 to Dec-26 | Sep-26 | Dec-26 | 4 | Milestone | Digital operations, security and service transition accepted | High |  | AFGHSP_Kenya_DOS Workplan Template.xlsx > tab 7 'Implementation Timeline' (Gantt)
Kenya | KEN06 | Sep-26 to Dec-26 | Sep-26 | Dec-26 | 4 | Milestone | HIS certification, hosting and administration capability transferred | High |  | AFGHSP_Kenya_DOS Workplan Template.xlsx > tab 7 'Implementation Timeline' (Gantt)
Kenya | KEN07 | Sep-26 to Dec-26 | Sep-26 | Dec-26 | 4 | Milestone | Sustainability financing and institutionalization package submitted | High |  | AFGHSP_Kenya_DOS Workplan Template.xlsx > tab 7 'Implementation Timeline' (Gantt)
Kenya | MKEN0 | Sep-26 to Oct-26 | Sep-26 | Oct-26 | 2 | Mobilization (not in budget) | Program mobilization and implementation governance operational | High |  | AFGHSP_Kenya_DOS Workplan Template.xlsx > tab 7 'Implementation Timeline' (Gantt)
Lesotho | LES01 | Oct-26 to Jan-27 | Oct-26 | Jan-27 | 4 | Milestone | OpenELIS Design, Migration & Production Readiness Validated | High |  | AFGHSP_Lesotho_Workplan_Revised_Template.xlsx > tab 3 'Implementation Timeline' (Gantt)
Lesotho | LES02 | Oct-26 to Mar-27 | Oct-26 | Mar-27 | 6 | Milestone | Supply-Chain Implementation Capacity Established | High |  | AFGHSP_Lesotho_Workplan_Revised_Template.xlsx > tab 3 'Implementation Timeline' (Gantt)
Lesotho | LES03 | Oct-26 to Mar-27 | Oct-26 | Mar-27 | 6 | Milestone | eLMIS Readiness, Commodity Baseline & Quantification Package Validated | High |  | AFGHSP_Lesotho_Workplan_Revised_Template.xlsx > tab 3 'Implementation Timeline' (Gantt)
Lesotho | LES04 | Oct-26 to Mar-27 | Oct-26 | Mar-27 | 6 | Milestone | iHRIS Workforce Data Standardization | High |  | AFGHSP_Lesotho_Workplan_Revised_Template.xlsx > tab 3 'Implementation Timeline' (Gantt)
Lesotho | LES05 | Oct-26 to Mar-27 | Oct-26 | Mar-27 | 6 | Milestone | National Analytics & CQI Information Platforms Operational and Used | High |  | AFGHSP_Lesotho_Workplan_Revised_Template.xlsx > tab 3 'Implementation Timeline' (Gantt)
Lesotho | LES06 | Oct-26 to Mar-27 | Oct-26 | Mar-27 | 6 | Milestone | Digital-Health Governance, Cybersecurity & Country-Ownership Roadmap Established | High |  | AFGHSP_Lesotho_Workplan_Revised_Template.xlsx > tab 3 'Implementation Timeline' (Gantt)
Lesotho | LES07 | Oct-26 to Mar-27 | Oct-26 | Mar-27 | 6 | Milestone | Informed-push process transitioned to a fully eLMIS workflow and national reporting integration | High |  | AFGHSP_Lesotho_Workplan_Revised_Template.xlsx > tab 3 'Implementation Timeline' (Gantt)
Lesotho | MLES0 | Oct-26 to Oct-26 | Oct-26 | Oct-26 | 1 | Mobilization (not in budget) | Mobilization & Operational Readiness | High |  | AFGHSP_Lesotho_Workplan_Revised_Template.xlsx > tab 3 'Implementation Timeline' (Gantt)
Madagascar | MAD01 | Oct-26 to Feb-27 | Oct-26 | Feb-27 | 5 | Milestone | DEPSI capacity for routine DHIS2 administration, maintenance and recovery established through national helpdesk | High |  | AFGHSP_Madagascar_Workplan_Revised_Template.xlsx > tab 3 'Implementation Timeline' (Gantt)
Madagascar | MAD02 | Oct-26 to Feb-27 | Oct-26 | Feb-27 | 5 | Milestone | Program Dashboards, MoU Monitoring & HIS Governance Used in Routine Oversight | High |  | AFGHSP_Madagascar_Workplan_Revised_Template.xlsx > tab 3 'Implementation Timeline' (Gantt)
Madagascar | MAD03 | Oct-26 to Apr-27 | Oct-26 | Apr-27 | 7 | Milestone | Mobile scorecard usage-monitoring results demonstrate active use in three districts | High |  | AFGHSP_Madagascar_Workplan_Revised_Template.xlsx > tab 3 'Implementation Timeline' (Gantt)
Madagascar | MAD04 | Oct-26 to Sep-27 | Oct-26 | Sep-27 | 12 | Milestone | USG portfolio assessment and electronic oversight platform operational | High |  | AFGHSP_Madagascar_Workplan_Revised_Template.xlsx > tab 3 'Implementation Timeline' (Gantt)
Madagascar | MAD05 | Jan-27 to Jun-27 | Jan-27 | Jun-27 | 6 | Milestone | GHS investigation indicators, dashboards and analytics toolkit operational | High |  | AFGHSP_Madagascar_Workplan_Revised_Template.xlsx > tab 3 'Implementation Timeline' (Gantt)
Madagascar | MAD06 | Oct-26 to May-27 | Oct-26 | May-27 | 8 | Milestone | Extended GAS application requirements validated and government users demonstrate competency | High |  | AFGHSP_Madagascar_Workplan_Revised_Template.xlsx > tab 3 'Implementation Timeline' (Gantt)
Madagascar | MAD07 | Nov-26 to Jun-27 | Nov-26 | Jun-27 | 8 | Milestone | Electronic Master Facility List Operationalization | High |  | AFGHSP_Madagascar_Workplan_Revised_Template.xlsx > tab 3 'Implementation Timeline' (Gantt)
Madagascar | MAD08 | Oct-26 to Jun-27 | Oct-26 | Jun-27 | 9 | Milestone | RMA module test deployment completed in two districts with competent users | High |  | AFGHSP_Madagascar_Workplan_Revised_Template.xlsx > tab 3 'Implementation Timeline' (Gantt)
Madagascar | MAD09 | Nov-26 to Jun-27 | Nov-26 | Jun-27 | 8 | Milestone | Interoperability Sandbox & Mpox Data Exchange | High |  | AFGHSP_Madagascar_Workplan_Revised_Template.xlsx > tab 3 'Implementation Timeline' (Gantt)
Madagascar | MAD10 | Nov-26 to Jun-27 | Nov-26 | Jun-27 | 8 | Milestone | Standard Case-Investigation Instruments & Investigator Competency Established | High |  | AFGHSP_Madagascar_Workplan_Revised_Template.xlsx > tab 3 'Implementation Timeline' (Gantt)
Madagascar | MAD11 | Dec-26 to Jul-27 | Dec-26 | Jul-27 | 8 | Milestone | Program & Logistics Data-Quality Improvement Demonstrated | High |  | AFGHSP_Madagascar_Workplan_Revised_Template.xlsx > tab 3 'Implementation Timeline' (Gantt)
Madagascar | MMAD0 | Oct-26 to Nov-26 | Oct-26 | Nov-26 | 2 | Mobilization (not in budget) | Mobilization & Operational Readiness | High |  | AFGHSP_Madagascar_Workplan_Revised_Template.xlsx > tab 3 'Implementation Timeline' (Gantt)
Moldova | MMOL0 | Sep-26 to Dec-26 | Sep-26 | Dec-26 | 4 | Mobilization (not in budget) | Mobilization and operational readiness | High |  | AFGHSP_Moldova_DOS Workplan Template.xlsx > tab 7 'Implementation Timeline' (Gantt)
Moldova | MOL01 | Sep-26 to May-27 | Sep-26 | May-27 | 9 | Milestone | Hospital Passport data governance, pipelines and analytics operational | High |  | AFGHSP_Moldova_DOS Workplan Template.xlsx > tab 7 'Implementation Timeline' (Gantt)
Moldova | MOL02 | Sep-26 to Aug-27 | Sep-26 | Aug-27 | 12 | Milestone | One Health AMR surveillance and lab-to-surveillance turnaround | High |  | AFGHSP_Moldova_DOS Workplan Template.xlsx > tab 7 'Implementation Timeline' (Gantt)
Moldova | MOL03 | Sep-26 to May-27 | Sep-26 | May-27 | 9 | Milestone | Domestic financing and costing tools in use | High |  | AFGHSP_Moldova_DOS Workplan Template.xlsx > tab 7 'Implementation Timeline' (Gantt)
Moldova | MOL04 | Sep-26 to Jun-27 | Sep-26 | Jun-27 | 10 | Milestone | AMS governance and quality-management mechanisms operational | High |  | AFGHSP_Moldova_DOS Workplan Template.xlsx > tab 7 'Implementation Timeline' (Gantt)
Moldova | MOL05 | Sep-26 to Jun-27 | Sep-26 | Jun-27 | 10 | Milestone | AMS workforce competency and facility-level application | High |  | AFGHSP_Moldova_DOS Workplan Template.xlsx > tab 7 'Implementation Timeline' (Gantt)
Namibia | MNAM0 | Oct-26 to Oct-26 | Oct-26 | Oct-26 | 1 | Mobilization (not in budget) | Mobilization & Operational Readiness | High |  | AFGHSP_Namibia_DOS Workplan Template.xlsx > tab 3 'Implementation Timeline' (Gantt)
Namibia | NAM01 | Oct-26 to Dec-26 | Oct-26 | Dec-26 | 3 | Milestone | HIS Stewardship, Support & Administrator Capacity Operational | High |  | AFGHSP_Namibia_DOS Workplan Template.xlsx > tab 3 'Implementation Timeline' (Gantt)
Namibia | NAM02 | Oct-26 to Dec-26 | Oct-26 | Dec-26 | 3 | Milestone | IDSR dashboard and automated outbreak analytics pipelines operational and tested | High |  | AFGHSP_Namibia_DOS Workplan Template.xlsx > tab 3 'Implementation Timeline' (Gantt)
Namibia | NAM03 | Oct-26 to Mar-27 | Oct-26 | Mar-27 | 6 | Milestone | HIV/TB SI Tools & Data-Use Capacity Validated | High |  | AFGHSP_Namibia_DOS Workplan Template.xlsx > tab 3 'Implementation Timeline' (Gantt)
Namibia | NAM04 | Oct-26 to Feb-27 | Oct-26 | Feb-27 | 5 | Milestone | Surveillance & Outbreak-Analytics Readiness and Epidemiology Capacity Established | High |  | AFGHSP_Namibia_DOS Workplan Template.xlsx > tab 3 'Implementation Timeline' (Gantt)
Namibia | NAM05 | Oct-26 to Mar-27 | Oct-26 | Mar-27 | 6 | Milestone | Commodity Analytics, Forecasting & Supply Planning Applied | High |  | AFGHSP_Namibia_DOS Workplan Template.xlsx > tab 3 'Implementation Timeline' (Gantt)
Namibia | NAM06 | Oct-26 to Mar-27 | Oct-26 | Mar-27 | 6 | Milestone | Supply-Chain Procedures & Institutional Capacity Implemented | High |  | AFGHSP_Namibia_DOS Workplan Template.xlsx > tab 3 'Implementation Timeline' (Gantt)
Namibia | NAM07 | Jan-27 to Mar-27 | Jan-27 | Mar-27 | 3 | Milestone | Namibia Digital Community Health System Pilot Deployed & Operational | High |  | AFGHSP_Namibia_DOS Workplan Template.xlsx > tab 3 'Implementation Timeline' (Gantt)
Namibia | NAM08 | Oct-26 to Mar-27 | Oct-26 | Mar-27 | 6 | Milestone | HIS data-quality and data-use dashboards operational and used in routine reviews | Medium | Gantt bar ends Feb-27, but Planned End on the timeline tab and the Workplan tab both say Mar-27; recommended window follows the two text sources. | AFGHSP_Namibia_DOS Workplan Template.xlsx > tab 3 'Implementation Timeline' (Gantt)
Namibia | NAM09 | Oct-26 to Mar-27 | Oct-26 | Mar-27 | 6 | Milestone | HIV/TB SI support demonstrates data-quality improvement with approval-risk mitigation | High |  | AFGHSP_Namibia_DOS Workplan Template.xlsx > tab 3 'Implementation Timeline' (Gantt)
Namibia | NAM10 | Oct-26 to Mar-27 | Oct-26 | Mar-27 | 6 | Milestone | Pharmaceutical Digital Systems & EDT Support Operational | High |  | AFGHSP_Namibia_DOS Workplan Template.xlsx > tab 3 'Implementation Timeline' (Gantt)
Niger | MNIG0 | Oct-26 to Oct-26 | Oct-26 | Oct-26 | 1 | Mobilization (not in budget) | Program mobilization and implementation governance operational | High |  | AFGHSP_Niger_Workplan_Revised_Template.xlsx > tab 3 'Implementation Timeline' (Gantt)
Niger | NIG01 | Oct-26 to Feb-27 | Oct-26 | Feb-27 | 5 | Milestone | Decision-Support Analytics Operational & Independently Used by DSRE | High |  | AFGHSP_Niger_Workplan_Revised_Template.xlsx > tab 3 'Implementation Timeline' (Gantt)
Niger | NIG02 | Oct-26 to Feb-27 | Oct-26 | Feb-27 | 5 | Milestone | MoH-Owned HIS Helpdesk & e-Learning Capability Operational | High |  | AFGHSP_Niger_Workplan_Revised_Template.xlsx > tab 3 'Implementation Timeline' (Gantt)
Niger | NIG03 | Oct-26 to Apr-27 | Oct-26 | Apr-27 | 7 | Milestone | mSupply–OpenFn–DHIS2 Integration Operational in Production | High |  | AFGHSP_Niger_Workplan_Revised_Template.xlsx > tab 3 'Implementation Timeline' (Gantt)
Niger | NIG04 | Oct-26 to Apr-27 | Oct-26 | Apr-27 | 7 | Milestone | Ten named public/private priority pharmacies actively use mSupply with verified data quality | High |  | AFGHSP_Niger_Workplan_Revised_Template.xlsx > tab 3 'Implementation Timeline' (Gantt)
Niger | NIG05 | Oct-26 to May-27 | Oct-26 | May-27 | 8 | Milestone | DHIS2 Platform Upgrade, Resilience & Recovery Verified | High |  | AFGHSP_Niger_Workplan_Revised_Template.xlsx > tab 3 'Implementation Timeline' (Gantt)
Niger | NIG06 | Oct-26 to May-27 | Oct-26 | May-27 | 8 | Milestone | GHS Data Governance, DQA & 7-1-7 Timeliness Improvement Demonstrated | High |  | AFGHSP_Niger_Workplan_Revised_Template.xlsx > tab 3 'Implementation Timeline' (Gantt)
Niger | NIG07 | Oct-26 to Jul-27 | Oct-26 | Jul-27 | 10 | Milestone | Malaria & MCH Data-Quality Improvement | High |  | AFGHSP_Niger_Workplan_Revised_Template.xlsx > tab 3 'Implementation Timeline' (Gantt)
Niger | NIG08 | Nov-26 to Jul-27 | Nov-26 | Jul-27 | 9 | Milestone | Priority Interoperability Use Cases Validated | High |  | AFGHSP_Niger_Workplan_Revised_Template.xlsx > tab 3 'Implementation Timeline' (Gantt)
Niger | NIG09 | Oct-26 to Jul-27 | Oct-26 | Jul-27 | 10 | Milestone | Laboratory Digitization & Specimen Traceability | High |  | AFGHSP_Niger_Workplan_Revised_Template.xlsx > tab 3 'Implementation Timeline' (Gantt)
Niger | NIG10 | Oct-26 to Aug-27 | Oct-26 | Aug-27 | 11 | Milestone | Digital Governance, Transition & Sustainability Framework Operational | High |  | AFGHSP_Niger_Workplan_Revised_Template.xlsx > tab 3 'Implementation Timeline' (Gantt)
Nigeria | MNRA0 | Oct-26 to Dec-26 | Oct-26 | Dec-26 | 3 | Mobilization (not in budget) | Mobilization and Operational Readiness | High |  | AFGHSP_Nigeria_Workplan_Revised_Template.xlsx > tab 3 'Implementation Timeline' (Gantt)
Nigeria | NRA01 | Oct-26 to Dec-26 | Oct-26 | Dec-26 | 3 | Milestone | Priority service performance dashboards functional and actively used | High |  | AFGHSP_Nigeria_Workplan_Revised_Template.xlsx > tab 3 'Implementation Timeline' (Gantt)
Nigeria | NRA02 | Oct-26 to Dec-26 | Oct-26 | Dec-26 | 3 | Milestone | Data quality and corrective-action cycle validated | High |  | AFGHSP_Nigeria_Workplan_Revised_Template.xlsx > tab 3 'Implementation Timeline' (Gantt)
Nigeria | NRA03 | Oct-26 to Dec-26 | Oct-26 | Dec-26 | 3 | Milestone | Linkage of Community/PHC/referral data with closed systems loops | High |  | AFGHSP_Nigeria_Workplan_Revised_Template.xlsx > tab 3 'Implementation Timeline' (Gantt)
Nigeria | NRA04 | Oct-26 to Dec-26 | Oct-26 | Dec-26 | 3 | Milestone | Priority interoperability use cases validated end-to-end | High |  | AFGHSP_Nigeria_Workplan_Revised_Template.xlsx > tab 3 'Implementation Timeline' (Gantt)
Nigeria | NRA05 | Oct-26 to Dec-26 | Oct-26 | Dec-26 | 3 | Milestone | Unified data pipelines, repositories, and analytics products operational and used for decisions | High |  | AFGHSP_Nigeria_Workplan_Revised_Template.xlsx > tab 3 'Implementation Timeline' (Gantt)
Nigeria | NRA06 | Oct-26 to Dec-26 | Oct-26 | Dec-26 | 3 | Milestone | Reporting quality, timeliness & concordance | High |  | AFGHSP_Nigeria_Workplan_Revised_Template.xlsx > tab 3 'Implementation Timeline' (Gantt)
Nigeria | NRA07 | Oct-26 to Dec-26 | Oct-26 | Dec-26 | 3 | Milestone | Operational AWS-hosted infrastructure with continuous uptime monitoring and support mechanisms | High |  | AFGHSP_Nigeria_Workplan_Revised_Template.xlsx > tab 3 'Implementation Timeline' (Gantt)
Nigeria | NRA08 | Oct-26 to Dec-26 | Oct-26 | Dec-26 | 3 | Milestone | System reliability, cybersecurity, and user support controls operationalized | High |  | AFGHSP_Nigeria_Workplan_Revised_Template.xlsx > tab 3 'Implementation Timeline' (Gantt)
Nigeria | NRA09 | Oct-26 to Dec-26 | Oct-26 | Dec-26 | 3 | Milestone | LAMISPlus-to-NDR outbreak-intelligence flow supports seven-day identification and timely updates | High |  | AFGHSP_Nigeria_Workplan_Revised_Template.xlsx > tab 3 'Implementation Timeline' (Gantt)
Nigeria | NRA10 | Oct-26 to Dec-26 | Oct-26 | Dec-26 | 3 | Milestone | Alert escalation & response workflow functioning | High |  | AFGHSP_Nigeria_Workplan_Revised_Template.xlsx > tab 3 'Implementation Timeline' (Gantt)
Nigeria | NRA11 | Oct-26 to Dec-26 | Oct-26 | Dec-26 | 3 | Milestone | Transition governance & handover readiness | High |  | AFGHSP_Nigeria_Workplan_Revised_Template.xlsx > tab 3 'Implementation Timeline' (Gantt)
Nigeria | NRA12 | Oct-26 to Dec-26 | Oct-26 | Dec-26 | 3 | Milestone | Domestic financing, PFM & governance use | High |  | AFGHSP_Nigeria_Workplan_Revised_Template.xlsx > tab 3 'Implementation Timeline' (Gantt)

## Monthly (long)
Country / Budget | Milestone | Month | Month (date) | Type | Confidence
Botswana | BOT01 | Oct-26 | 2026-10-01 | Milestone | High
Botswana | BOT01 | Nov-26 | 2026-11-01 | Milestone | High
Botswana | BOT01 | Dec-26 | 2026-12-01 | Milestone | High
Botswana | BOT02 | Oct-26 | 2026-10-01 | Milestone | High
Botswana | BOT02 | Nov-26 | 2026-11-01 | Milestone | High
Botswana | BOT02 | Dec-26 | 2026-12-01 | Milestone | High
Botswana | BOT03 | Oct-26 | 2026-10-01 | Milestone | High
Botswana | BOT03 | Nov-26 | 2026-11-01 | Milestone | High
Botswana | BOT04 | Oct-26 | 2026-10-01 | Milestone | High
Botswana | BOT04 | Nov-26 | 2026-11-01 | Milestone | High
Botswana | BOT04 | Dec-26 | 2026-12-01 | Milestone | High
Botswana | BOT05 | Oct-26 | 2026-10-01 | Milestone | High
Botswana | BOT05 | Nov-26 | 2026-11-01 | Milestone | High
Botswana | BOT05 | Dec-26 | 2026-12-01 | Milestone | High
Botswana | BOT06 | Oct-26 | 2026-10-01 | Milestone | High
Botswana | BOT06 | Nov-26 | 2026-11-01 | Milestone | High
Botswana | BOT06 | Dec-26 | 2026-12-01 | Milestone | High
Botswana | MBOT00 | Sep-26 | 2026-09-01 | Milestone | High
Burundi | BUR01 | Sep-26 | 2026-09-01 | Milestone | High
Burundi | BUR01 | Oct-26 | 2026-10-01 | Milestone | High
Burundi | BUR01 | Nov-26 | 2026-11-01 | Milestone | High
Burundi | BUR01 | Dec-26 | 2026-12-01 | Milestone | High
Burundi | BUR02 | Oct-26 | 2026-10-01 | Milestone | High
Burundi | BUR02 | Nov-26 | 2026-11-01 | Milestone | High
Burundi | BUR02 | Dec-26 | 2026-12-01 | Milestone | High
Burundi | BUR02 | Jan-27 | 2027-01-01 | Milestone | High
Burundi | BUR02 | Feb-27 | 2027-02-01 | Milestone | High
Burundi | BUR03 | Oct-26 | 2026-10-01 | Milestone | High
Burundi | BUR03 | Nov-26 | 2026-11-01 | Milestone | High
Burundi | BUR03 | Dec-26 | 2026-12-01 | Milestone | High
Burundi | BUR03 | Jan-27 | 2027-01-01 | Milestone | High
Burundi | BUR03 | Feb-27 | 2027-02-01 | Milestone | High
Burundi | BUR04 | Sep-26 | 2026-09-01 | Milestone | High
Burundi | BUR04 | Oct-26 | 2026-10-01 | Milestone | High
Burundi | BUR04 | Nov-26 | 2026-11-01 | Milestone | High
Burundi | BUR04 | Dec-26 | 2026-12-01 | Milestone | High
Burundi | BUR04 | Jan-27 | 2027-01-01 | Milestone | High
Burundi | BUR04 | Feb-27 | 2027-02-01 | Milestone | High
Burundi | BUR05 | Sep-26 | 2026-09-01 | Milestone | High
Burundi | BUR05 | Oct-26 | 2026-10-01 | Milestone | High
Burundi | BUR05 | Nov-26 | 2026-11-01 | Milestone | High
Burundi | BUR05 | Dec-26 | 2026-12-01 | Milestone | High
Burundi | BUR05 | Jan-27 | 2027-01-01 | Milestone | High
Burundi | BUR05 | Feb-27 | 2027-02-01 | Milestone | High
Burundi | BUR06 | Sep-26 | 2026-09-01 | Milestone | High
Burundi | BUR06 | Oct-26 | 2026-10-01 | Milestone | High
Burundi | BUR06 | Nov-26 | 2026-11-01 | Milestone | High
Burundi | BUR06 | Dec-26 | 2026-12-01 | Milestone | High
Burundi | BUR06 | Jan-27 | 2027-01-01 | Milestone | High
Burundi | BUR06 | Feb-27 | 2027-02-01 | Milestone | High
Burundi | BUR07 | Sep-26 | 2026-09-01 | Milestone | High
Burundi | BUR07 | Oct-26 | 2026-10-01 | Milestone | High
Burundi | BUR07 | Nov-26 | 2026-11-01 | Milestone | High
Burundi | BUR07 | Dec-26 | 2026-12-01 | Milestone | High
Burundi | BUR07 | Jan-27 | 2027-01-01 | Milestone | High
Burundi | BUR07 | Feb-27 | 2027-02-01 | Milestone | High
Burundi | BUR08 | Sep-26 | 2026-09-01 | Milestone | High
Burundi | BUR08 | Oct-26 | 2026-10-01 | Milestone | High
Burundi | BUR08 | Nov-26 | 2026-11-01 | Milestone | High
Burundi | BUR08 | Dec-26 | 2026-12-01 | Milestone | High
Burundi | BUR08 | Jan-27 | 2027-01-01 | Milestone | High
Burundi | BUR08 | Feb-27 | 2027-02-01 | Milestone | High
Burundi | BUR08 | Mar-27 | 2027-03-01 | Milestone | High
Burundi | MBUR0 | Sep-26 | 2026-09-01 | Mobilization (not in budget) | High
Burundi | MBUR0 | Oct-26 | 2026-10-01 | Mobilization (not in budget) | High
Burundi | MBUR0 | Nov-26 | 2026-11-01 | Mobilization (not in budget) | High
Burundi | MBUR0 | Dec-26 | 2026-12-01 | Mobilization (not in budget) | High
CORE G2G | MM0.3 | Sep-26 | 2026-09-01 | Mobilization (not in budget) | High
CORE G2G | MM0.3 | Oct-26 | 2026-10-01 | Mobilization (not in budget) | High
CORE G2G | MM0.3 | Nov-26 | 2026-11-01 | Mobilization (not in budget) | High
CORE G2G | MM0.3 | Dec-26 | 2026-12-01 | Mobilization (not in budget) | High
CORE G2G | T1.5 | Sep-26 | 2026-09-01 | Milestone | Medium
CORE G2G | T1.5 | Oct-26 | 2026-10-01 | Milestone | Medium
CORE G2G | T1.5 | Nov-26 | 2026-11-01 | Milestone | Medium
CORE G2G | T1.5 | Dec-26 | 2026-12-01 | Milestone | Medium
CORE G2G | T1.5 | Jan-27 | 2027-01-01 | Milestone | Medium
CORE G2G | T1.5 | Feb-27 | 2027-02-01 | Milestone | Medium
CORE G2G | T1.5 | Mar-27 | 2027-03-01 | Milestone | Medium
CORE G2G | T1.5 | Apr-27 | 2027-04-01 | Milestone | Medium
CORE G2G | T1.5 | May-27 | 2027-05-01 | Milestone | Medium
CORE G2G | T1.5 | Jun-27 | 2027-06-01 | Milestone | Medium
CORE G2G | T1.5 | Jul-27 | 2027-07-01 | Milestone | Medium
CORE G2G | T1.5 | Aug-27 | 2027-08-01 | Milestone | Medium
CORE G2G | T1.5 | Sep-27 | 2027-09-01 | Milestone | Medium
CORE-EMR ECHIS | C2 | Oct-26 | 2026-10-01 | Milestone | Medium
CORE-EMR ECHIS | C2 | Nov-26 | 2026-11-01 | Milestone | Medium
CORE-EMR ECHIS | C2 | Dec-26 | 2026-12-01 | Milestone | Medium
CORE-EMR ECHIS | C2 | Jan-27 | 2027-01-01 | Milestone | Medium
CORE-EMR ECHIS | C2 | Feb-27 | 2027-02-01 | Milestone | Medium
CORE-EMR ECHIS | C2 | Mar-27 | 2027-03-01 | Milestone | Medium
CORE-EMR ECHIS | C2 | Apr-27 | 2027-04-01 | Milestone | Medium
CORE-EMR ECHIS | C2 | May-27 | 2027-05-01 | Milestone | Medium
CORE-EMR ECHIS | C2 | Jun-27 | 2027-06-01 | Milestone | Medium
CORE-EMR ECHIS | C2 | Jul-27 | 2027-07-01 | Milestone | Medium
CORE-EMR ECHIS | C2 | Aug-27 | 2027-08-01 | Milestone | Medium
CORE-EMR ECHIS | C2 | Sep-27 | 2027-09-01 | Milestone | Medium
CORE-EMR ECHIS | MM0.1 | Sep-26 | 2026-09-01 | Mobilization (not in budget) | High
CORE-EMR ECHIS | MM0.1 | Oct-26 | 2026-10-01 | Mobilization (not in budget) | High
CORE-EMR ECHIS | MM0.1 | Nov-26 | 2026-11-01 | Mobilization (not in budget) | High
CORE-EMR ECHIS | MM0.1 | Dec-26 | 2026-12-01 | Mobilization (not in budget) | High
CORE-EMR ECHIS | MM0.2 | Sep-26 | 2026-09-01 | Mobilization (not in budget) | High
CORE-EMR ECHIS | MM0.2 | Oct-26 | 2026-10-01 | Mobilization (not in budget) | High
CORE-EMR ECHIS | MM0.2 | Nov-26 | 2026-11-01 | Mobilization (not in budget) | High
CORE-EMR ECHIS | MM0.2 | Dec-26 | 2026-12-01 | Mobilization (not in budget) | High
CORE-EMR ECHIS | T1.8 | Oct-26 | 2026-10-01 | Milestone | Medium
CORE-EMR ECHIS | T1.8 | Nov-26 | 2026-11-01 | Milestone | Medium
CORE-EMR ECHIS | T1.8 | Dec-26 | 2026-12-01 | Milestone | Medium
CORE-EMR ECHIS | T1.8 | Jan-27 | 2027-01-01 | Milestone | Medium
CORE-EMR ECHIS | T1.8 | Feb-27 | 2027-02-01 | Milestone | Medium
CORE-EMR ECHIS | T1.8 | Mar-27 | 2027-03-01 | Milestone | Medium
CORE-EMR ECHIS | T1.8 | Apr-27 | 2027-04-01 | Milestone | Medium
CORE-EMR ECHIS | T1.8 | May-27 | 2027-05-01 | Milestone | Medium
CORE-EMR ECHIS | T1.8 | Jun-27 | 2027-06-01 | Milestone | Medium
CORE-EMR ECHIS | T1.8 | Jul-27 | 2027-07-01 | Milestone | Medium
CORE-EMR ECHIS | T1.8 | Aug-27 | 2027-08-01 | Milestone | Medium
CORE-EMR ECHIS | T1.8 | Sep-27 | 2027-09-01 | Milestone | Medium
CORE-Ebola | E1 | Jan-27 | 2027-01-01 | Milestone | Medium
CORE-Ebola | E1 | Feb-27 | 2027-02-01 | Milestone | Medium
CORE-Ebola | E1 | Mar-27 | 2027-03-01 | Milestone | Medium
CORE-Ebola | E1 | Apr-27 | 2027-04-01 | Milestone | Medium
CORE-Ebola | E1 | May-27 | 2027-05-01 | Milestone | Medium
CORE-Ebola | E1 | Jun-27 | 2027-06-01 | Milestone | Medium
CORE-Ebola | E2 | Jan-27 | 2027-01-01 | Milestone | Medium
CORE-Ebola | E2 | Feb-27 | 2027-02-01 | Milestone | Medium
CORE-Ebola | E2 | Mar-27 | 2027-03-01 | Milestone | Medium
CORE-Ebola | E2 | Apr-27 | 2027-04-01 | Milestone | Medium
CORE-Ebola | E2 | May-27 | 2027-05-01 | Milestone | Medium
CORE-Ebola | E2 | Jun-27 | 2027-06-01 | Milestone | Medium
CORE-Ebola | E2 | Jul-27 | 2027-07-01 | Milestone | Medium
CORE-Ebola | E2 | Aug-27 | 2027-08-01 | Milestone | Medium
CORE-Ebola | E2 | Sep-27 | 2027-09-01 | Milestone | Medium
CORE-Ebola | E3 | Oct-26 | 2026-10-01 | Milestone | Medium
CORE-Ebola | E3 | Nov-26 | 2026-11-01 | Milestone | Medium
CORE-Ebola | E3 | Dec-26 | 2026-12-01 | Milestone | Medium
CORE-Ebola | E3 | Jan-27 | 2027-01-01 | Milestone | Medium
CORE-Ebola | E3 | Feb-27 | 2027-02-01 | Milestone | Medium
CORE-Ebola | E3 | Mar-27 | 2027-03-01 | Milestone | Medium
CORE-Ebola | E3 | Apr-27 | 2027-04-01 | Milestone | Medium
CORE-Ebola | E3 | May-27 | 2027-05-01 | Milestone | Medium
CORE-Ebola | E3 | Jun-27 | 2027-06-01 | Milestone | Medium
CORE-Ebola | E3 | Jul-27 | 2027-07-01 | Milestone | Medium
CORE-Ebola | E3 | Aug-27 | 2027-08-01 | Milestone | Medium
CORE-Ebola | E3 | Sep-27 | 2027-09-01 | Milestone | Medium
CORE-Ebola | MM0.6 | Oct-26 | 2026-10-01 | Mobilization (not in budget) | High
CORE-Ebola | MM0.6 | Nov-26 | 2026-11-01 | Mobilization (not in budget) | High
CORE-Ebola | MM0.6 | Dec-26 | 2026-12-01 | Mobilization (not in budget) | High
CORE-Ebola | T1.4 | Jan-27 | 2027-01-01 | Milestone | High
CORE-Ebola | T1.4 | Feb-27 | 2027-02-01 | Milestone | High
CORE-Ebola | T1.4 | Mar-27 | 2027-03-01 | Milestone | High
CORE-Ebola | T1.4 | Apr-27 | 2027-04-01 | Milestone | High
CORE-Ebola | T1.4 | May-27 | 2027-05-01 | Milestone | High
CORE-Ebola | T1.4 | Jun-27 | 2027-06-01 | Milestone | High
CORE-Ebola | T1.4 | Jul-27 | 2027-07-01 | Milestone | High
CORE-Ebola | T1.4 | Aug-27 | 2027-08-01 | Milestone | High
CORE-Ebola | T1.4 | Sep-27 | 2027-09-01 | Milestone | High
CORE-HIC | C1a | Sep-26 | 2026-09-01 | Milestone | Medium
CORE-HIC | C1a | Oct-26 | 2026-10-01 | Milestone | Medium
CORE-HIC | C1a | Nov-26 | 2026-11-01 | Milestone | Medium
CORE-HIC | C1a | Dec-26 | 2026-12-01 | Milestone | Medium
CORE-HIC | C1a | Jan-27 | 2027-01-01 | Milestone | Medium
CORE-HIC | C1a | Feb-27 | 2027-02-01 | Milestone | Medium
CORE-HIC | C1a | Mar-27 | 2027-03-01 | Milestone | Medium
CORE-HIC | C1b | Sep-26 | 2026-09-01 | Milestone | Medium
CORE-HIC | C1b | Oct-26 | 2026-10-01 | Milestone | Medium
CORE-HIC | C1b | Nov-26 | 2026-11-01 | Milestone | Medium
CORE-HIC | C1b | Dec-26 | 2026-12-01 | Milestone | Medium
CORE-HIC | C1b | Jan-27 | 2027-01-01 | Milestone | Medium
CORE-HIC | C1b | Feb-27 | 2027-02-01 | Milestone | Medium
CORE-HIC | C1b | Mar-27 | 2027-03-01 | Milestone | Medium
CORE-HIC | C1b | Apr-27 | 2027-04-01 | Milestone | Medium
CORE-HIC | C1b | May-27 | 2027-05-01 | Milestone | Medium
CORE-HIC | C1b | Jun-27 | 2027-06-01 | Milestone | Medium
CORE-HIC | C1b | Jul-27 | 2027-07-01 | Milestone | Medium
CORE-HIC | C1b | Aug-27 | 2027-08-01 | Milestone | Medium
CORE-HIC | MM0.5 | Sep-26 | 2026-09-01 | Mobilization (not in budget) | High
CORE-HIC | MM0.5 | Oct-26 | 2026-10-01 | Mobilization (not in budget) | High
CORE-HIC | MM0.5 | Nov-26 | 2026-11-01 | Mobilization (not in budget) | High
CORE-HIC | MM0.5 | Dec-26 | 2026-12-01 | Mobilization (not in budget) | High
CORE-Supply Chain | C5 | Oct-26 | 2026-10-01 | Milestone | High
CORE-Supply Chain | C5 | Nov-26 | 2026-11-01 | Milestone | High
CORE-Supply Chain | C5 | Dec-26 | 2026-12-01 | Milestone | High
CORE-Supply Chain | C5 | Jan-27 | 2027-01-01 | Milestone | High
CORE-Supply Chain | C5 | Feb-27 | 2027-02-01 | Milestone | High
CORE-Supply Chain | C5 | Mar-27 | 2027-03-01 | Milestone | High
CORE-Supply Chain | C5 | Apr-27 | 2027-04-01 | Milestone | High
CORE-Supply Chain | C5 | May-27 | 2027-05-01 | Milestone | High
CORE-Supply Chain | C5 | Jun-27 | 2027-06-01 | Milestone | High
CORE-Supply Chain | C5 | Jul-27 | 2027-07-01 | Milestone | High
CORE-Supply Chain | C5 | Aug-27 | 2027-08-01 | Milestone | High
CORE-Supply Chain | C5 | Sep-27 | 2027-09-01 | Milestone | High
CORE-Supply Chain | C6 | Oct-26 | 2026-10-01 | Milestone | High
CORE-Supply Chain | C6 | Nov-26 | 2026-11-01 | Milestone | High
CORE-Supply Chain | C6 | Dec-26 | 2026-12-01 | Milestone | High
CORE-Supply Chain | C6 | Jan-27 | 2027-01-01 | Milestone | High
CORE-Supply Chain | C6 | Feb-27 | 2027-02-01 | Milestone | High
CORE-Supply Chain | C6 | Mar-27 | 2027-03-01 | Milestone | High
CORE-Supply Chain | C6 | Apr-27 | 2027-04-01 | Milestone | High
CORE-Supply Chain | C6 | May-27 | 2027-05-01 | Milestone | High
CORE-Supply Chain | C6 | Jun-27 | 2027-06-01 | Milestone | High
CORE-Supply Chain | C6 | Jul-27 | 2027-07-01 | Milestone | High
CORE-Supply Chain | C6 | Aug-27 | 2027-08-01 | Milestone | High
CORE-Supply Chain | C6 | Sep-27 | 2027-09-01 | Milestone | High
CORE-Supply Chain | C7 | Oct-26 | 2026-10-01 | Milestone | High
CORE-Supply Chain | C7 | Nov-26 | 2026-11-01 | Milestone | High
CORE-Supply Chain | C7 | Dec-26 | 2026-12-01 | Milestone | High
CORE-Supply Chain | C7 | Jan-27 | 2027-01-01 | Milestone | High
CORE-Supply Chain | C7 | Feb-27 | 2027-02-01 | Milestone | High
CORE-Supply Chain | C7 | Mar-27 | 2027-03-01 | Milestone | High
CORE-Supply Chain | C7 | Apr-27 | 2027-04-01 | Milestone | High
CORE-Supply Chain | C7 | May-27 | 2027-05-01 | Milestone | High
CORE-Supply Chain | C7 | Jun-27 | 2027-06-01 | Milestone | High
CORE-Supply Chain | C7 | Jul-27 | 2027-07-01 | Milestone | High
CORE-Supply Chain | C7 | Aug-27 | 2027-08-01 | Milestone | High
CORE-Supply Chain | C7 | Sep-27 | 2027-09-01 | Milestone | High
CORE-Supply Chain | MM0.4 | Sep-26 | 2026-09-01 | Mobilization (not in budget) | High
CORE-Supply Chain | MM0.4 | Oct-26 | 2026-10-01 | Mobilization (not in budget) | High
CORE-Supply Chain | MM0.4 | Nov-26 | 2026-11-01 | Mobilization (not in budget) | High
CORE-Supply Chain | MM0.4 | Dec-26 | 2026-12-01 | Mobilization (not in budget) | High
CORE-Supply Chain | T1.6 | Oct-26 | 2026-10-01 | Milestone | High
CORE-Supply Chain | T1.6 | Nov-26 | 2026-11-01 | Milestone | High
CORE-Supply Chain | T1.6 | Dec-26 | 2026-12-01 | Milestone | High
CORE-Supply Chain | T1.6 | Jan-27 | 2027-01-01 | Milestone | High
CORE-Supply Chain | T1.6 | Feb-27 | 2027-02-01 | Milestone | High
CORE-Supply Chain | T1.6 | Mar-27 | 2027-03-01 | Milestone | High
CORE-Supply Chain | T1.6 | Apr-27 | 2027-04-01 | Milestone | High
CORE-Supply Chain | T1.6 | May-27 | 2027-05-01 | Milestone | High
CORE-Supply Chain | T1.6 | Jun-27 | 2027-06-01 | Milestone | High
CORE-Supply Chain | T1.6 | Jul-27 | 2027-07-01 | Milestone | High
CORE-Supply Chain | T1.6 | Aug-27 | 2027-08-01 | Milestone | High
CORE-Supply Chain | T1.6 | Sep-27 | 2027-09-01 | Milestone | High
DRC | DRC00 | Oct-26 | 2026-10-01 | Mobilization (not in budget) | Medium
DRC | DRC00 | Nov-26 | 2026-11-01 | Mobilization (not in budget) | Medium
DRC | DRC00 | Dec-26 | 2026-12-01 | Mobilization (not in budget) | Medium
DRC | DRC01 | Oct-26 | 2026-10-01 | Milestone | Medium
DRC | DRC01 | Nov-26 | 2026-11-01 | Milestone | Medium
DRC | DRC01 | Dec-26 | 2026-12-01 | Milestone | Medium
DRC | DRC01 | Jan-27 | 2027-01-01 | Milestone | Medium
DRC | DRC01 | Feb-27 | 2027-02-01 | Milestone | Medium
DRC | DRC02 | Oct-26 | 2026-10-01 | Milestone | Medium
DRC | DRC02 | Nov-26 | 2026-11-01 | Milestone | Medium
DRC | DRC02 | Dec-26 | 2026-12-01 | Milestone | Medium
DRC | DRC02 | Jan-27 | 2027-01-01 | Milestone | Medium
DRC | DRC02 | Feb-27 | 2027-02-01 | Milestone | Medium
DRC | DRC02 | Mar-27 | 2027-03-01 | Milestone | Medium
DRC | DRC03 | Oct-26 | 2026-10-01 | Milestone | Medium
DRC | DRC03 | Nov-26 | 2026-11-01 | Milestone | Medium
DRC | DRC03 | Dec-26 | 2026-12-01 | Milestone | Medium
DRC | DRC03 | Jan-27 | 2027-01-01 | Milestone | Medium
DRC | DRC03 | Feb-27 | 2027-02-01 | Milestone | Medium
DRC | DRC03 | Mar-27 | 2027-03-01 | Milestone | Medium
DRC | DRC04 | Oct-26 | 2026-10-01 | Milestone | Medium
DRC | DRC04 | Nov-26 | 2026-11-01 | Milestone | Medium
DRC | DRC04 | Dec-26 | 2026-12-01 | Milestone | Medium
DRC | DRC04 | Jan-27 | 2027-01-01 | Milestone | Medium
DRC | DRC04 | Feb-27 | 2027-02-01 | Milestone | Medium
DRC | DRC04 | Mar-27 | 2027-03-01 | Milestone | Medium
DRC | DRC04 | Apr-27 | 2027-04-01 | Milestone | Medium
DRC | DRC04 | May-27 | 2027-05-01 | Milestone | Medium
DRC | DRC04 | Jun-27 | 2027-06-01 | Milestone | Medium
DRC | DRC04 | Jul-27 | 2027-07-01 | Milestone | Medium
DRC | DRC04 | Aug-27 | 2027-08-01 | Milestone | Medium
DRC | DRC04 | Sep-27 | 2027-09-01 | Milestone | Medium
DRC | DRC05 | Oct-26 | 2026-10-01 | Milestone | Medium
DRC | DRC05 | Nov-26 | 2026-11-01 | Milestone | Medium
DRC | DRC05 | Dec-26 | 2026-12-01 | Milestone | Medium
DRC | DRC05 | Jan-27 | 2027-01-01 | Milestone | Medium
DRC | DRC05 | Feb-27 | 2027-02-01 | Milestone | Medium
DRC | DRC05 | Mar-27 | 2027-03-01 | Milestone | Medium
DRC | DRC05 | Apr-27 | 2027-04-01 | Milestone | Medium
DRC | DRC05 | May-27 | 2027-05-01 | Milestone | Medium
DRC | DRC05 | Jun-27 | 2027-06-01 | Milestone | Medium
DRC | DRC05 | Jul-27 | 2027-07-01 | Milestone | Medium
DRC | DRC05 | Aug-27 | 2027-08-01 | Milestone | Medium
DRC | DRC05 | Sep-27 | 2027-09-01 | Milestone | Medium
DRC | DRC06 | Oct-26 | 2026-10-01 | Milestone | Medium
DRC | DRC06 | Nov-26 | 2026-11-01 | Milestone | Medium
DRC | DRC06 | Dec-26 | 2026-12-01 | Milestone | Medium
DRC | DRC06 | Jan-27 | 2027-01-01 | Milestone | Medium
DRC | DRC06 | Feb-27 | 2027-02-01 | Milestone | Medium
DRC | DRC06 | Mar-27 | 2027-03-01 | Milestone | Medium
DRC | DRC06 | Apr-27 | 2027-04-01 | Milestone | Medium
DRC | DRC06 | May-27 | 2027-05-01 | Milestone | Medium
DRC | DRC06 | Jun-27 | 2027-06-01 | Milestone | Medium
DRC | DRC06 | Jul-27 | 2027-07-01 | Milestone | Medium
DRC | DRC06 | Aug-27 | 2027-08-01 | Milestone | Medium
DRC | DRC06 | Sep-27 | 2027-09-01 | Milestone | Medium
DRC | DRC07 | Oct-26 | 2026-10-01 | Milestone | Medium
DRC | DRC07 | Nov-26 | 2026-11-01 | Milestone | Medium
DRC | DRC07 | Dec-26 | 2026-12-01 | Milestone | Medium
DRC | DRC07 | Jan-27 | 2027-01-01 | Milestone | Medium
DRC | DRC07 | Feb-27 | 2027-02-01 | Milestone | Medium
DRC | DRC07 | Mar-27 | 2027-03-01 | Milestone | Medium
DRC | DRC07 | Apr-27 | 2027-04-01 | Milestone | Medium
DRC | DRC07 | May-27 | 2027-05-01 | Milestone | Medium
DRC | DRC07 | Jun-27 | 2027-06-01 | Milestone | Medium
DRC | DRC07 | Jul-27 | 2027-07-01 | Milestone | Medium
DRC | DRC07 | Aug-27 | 2027-08-01 | Milestone | Medium
DRC | DRC07 | Sep-27 | 2027-09-01 | Milestone | Medium
DRC | DRC08 | Oct-26 | 2026-10-01 | Milestone | Medium
DRC | DRC08 | Nov-26 | 2026-11-01 | Milestone | Medium
DRC | DRC08 | Dec-26 | 2026-12-01 | Milestone | Medium
DRC | DRC08 | Jan-27 | 2027-01-01 | Milestone | Medium
DRC | DRC08 | Feb-27 | 2027-02-01 | Milestone | Medium
DRC | DRC08 | Mar-27 | 2027-03-01 | Milestone | Medium
DRC | DRC08 | Apr-27 | 2027-04-01 | Milestone | Medium
DRC | DRC08 | May-27 | 2027-05-01 | Milestone | Medium
DRC | DRC08 | Jun-27 | 2027-06-01 | Milestone | Medium
DRC | DRC08 | Jul-27 | 2027-07-01 | Milestone | Medium
DRC | DRC08 | Aug-27 | 2027-08-01 | Milestone | Medium
DRC | DRC08 | Sep-27 | 2027-09-01 | Milestone | Medium
DRC | DRC09 | Oct-26 | 2026-10-01 | Milestone | Medium
DRC | DRC09 | Nov-26 | 2026-11-01 | Milestone | Medium
DRC | DRC09 | Dec-26 | 2026-12-01 | Milestone | Medium
DRC | DRC09 | Jan-27 | 2027-01-01 | Milestone | Medium
DRC | DRC09 | Feb-27 | 2027-02-01 | Milestone | Medium
DRC | DRC09 | Mar-27 | 2027-03-01 | Milestone | Medium
DRC | DRC09 | Apr-27 | 2027-04-01 | Milestone | Medium
DRC | DRC09 | May-27 | 2027-05-01 | Milestone | Medium
DRC | DRC09 | Jun-27 | 2027-06-01 | Milestone | Medium
DRC | DRC09 | Jul-27 | 2027-07-01 | Milestone | Medium
DRC | DRC09 | Aug-27 | 2027-08-01 | Milestone | Medium
DRC | DRC09 | Sep-27 | 2027-09-01 | Milestone | Medium
El Salvador | ELS01 | Oct-26 | 2026-10-01 | Milestone | High
El Salvador | ELS01 | Nov-26 | 2026-11-01 | Milestone | High
El Salvador | ELS01 | Dec-26 | 2026-12-01 | Milestone | High
El Salvador | ELS01 | Jan-27 | 2027-01-01 | Milestone | High
El Salvador | ELS01 | Feb-27 | 2027-02-01 | Milestone | High
El Salvador | ELS01 | Mar-27 | 2027-03-01 | Milestone | High
El Salvador | ELS01 | Apr-27 | 2027-04-01 | Milestone | High
El Salvador | ELS02 | Oct-26 | 2026-10-01 | Milestone | High
El Salvador | ELS02 | Nov-26 | 2026-11-01 | Milestone | High
El Salvador | ELS02 | Dec-26 | 2026-12-01 | Milestone | High
El Salvador | ELS02 | Jan-27 | 2027-01-01 | Milestone | High
El Salvador | ELS02 | Feb-27 | 2027-02-01 | Milestone | High
El Salvador | ELS02 | Mar-27 | 2027-03-01 | Milestone | High
El Salvador | ELS02 | Apr-27 | 2027-04-01 | Milestone | High
El Salvador | ELS03 | Oct-26 | 2026-10-01 | Milestone | High
El Salvador | ELS03 | Nov-26 | 2026-11-01 | Milestone | High
El Salvador | ELS03 | Dec-26 | 2026-12-01 | Milestone | High
El Salvador | ELS03 | Jan-27 | 2027-01-01 | Milestone | High
El Salvador | ELS03 | Feb-27 | 2027-02-01 | Milestone | High
El Salvador | ELS03 | Mar-27 | 2027-03-01 | Milestone | High
El Salvador | ELS03 | Apr-27 | 2027-04-01 | Milestone | High
El Salvador | ELS04 | Oct-26 | 2026-10-01 | Milestone | High
El Salvador | ELS04 | Nov-26 | 2026-11-01 | Milestone | High
El Salvador | ELS04 | Dec-26 | 2026-12-01 | Milestone | High
El Salvador | ELS04 | Jan-27 | 2027-01-01 | Milestone | High
El Salvador | ELS04 | Feb-27 | 2027-02-01 | Milestone | High
El Salvador | ELS04 | Mar-27 | 2027-03-01 | Milestone | High
El Salvador | ELS04 | Apr-27 | 2027-04-01 | Milestone | High
El Salvador | ELS05 | Oct-26 | 2026-10-01 | Milestone | High
El Salvador | ELS05 | Nov-26 | 2026-11-01 | Milestone | High
El Salvador | ELS05 | Dec-26 | 2026-12-01 | Milestone | High
El Salvador | ELS05 | Jan-27 | 2027-01-01 | Milestone | High
El Salvador | ELS05 | Feb-27 | 2027-02-01 | Milestone | High
El Salvador | ELS05 | Mar-27 | 2027-03-01 | Milestone | High
El Salvador | ELS05 | Apr-27 | 2027-04-01 | Milestone | High
El Salvador | MELS0 | Oct-26 | 2026-10-01 | Mobilization (not in budget) | High
El Salvador | MELS0 | Nov-26 | 2026-11-01 | Mobilization (not in budget) | High
Eswatini | ESW01 | Oct-26 | 2026-10-01 | Milestone | High
Eswatini | ESW01 | Nov-26 | 2026-11-01 | Milestone | High
Eswatini | ESW01 | Dec-26 | 2026-12-01 | Milestone | High
Eswatini | ESW02 | Oct-26 | 2026-10-01 | Milestone | High
Eswatini | ESW02 | Nov-26 | 2026-11-01 | Milestone | High
Eswatini | ESW02 | Dec-26 | 2026-12-01 | Milestone | High
Eswatini | ESW03 | Oct-26 | 2026-10-01 | Milestone | High
Eswatini | ESW03 | Nov-26 | 2026-11-01 | Milestone | High
Eswatini | ESW03 | Dec-26 | 2026-12-01 | Milestone | High
Eswatini | ESW04 | Oct-26 | 2026-10-01 | Milestone | High
Eswatini | ESW04 | Nov-26 | 2026-11-01 | Milestone | High
Eswatini | ESW04 | Dec-26 | 2026-12-01 | Milestone | High
Eswatini | ESW05 | Oct-26 | 2026-10-01 | Milestone | High
Eswatini | ESW05 | Nov-26 | 2026-11-01 | Milestone | High
Eswatini | ESW05 | Dec-26 | 2026-12-01 | Milestone | High
Eswatini | ESW06 | Oct-26 | 2026-10-01 | Milestone | High
Eswatini | ESW06 | Nov-26 | 2026-11-01 | Milestone | High
Eswatini | ESW06 | Dec-26 | 2026-12-01 | Milestone | High
Eswatini | ESW07 | Oct-26 | 2026-10-01 | Milestone | High
Eswatini | ESW07 | Nov-26 | 2026-11-01 | Milestone | High
Eswatini | ESW07 | Dec-26 | 2026-12-01 | Milestone | High
Eswatini | ESW08 | Oct-26 | 2026-10-01 | Milestone | High
Eswatini | ESW08 | Nov-26 | 2026-11-01 | Milestone | High
Eswatini | ESW08 | Dec-26 | 2026-12-01 | Milestone | High
Eswatini | MESW0 | Oct-26 | 2026-10-01 | Mobilization (not in budget) | High
Eswatini | MESW0 | Nov-26 | 2026-11-01 | Mobilization (not in budget) | High
Ethiopia | ETH01 | Sep-26 | 2026-09-01 | Milestone | Medium
Ethiopia | ETH01 | Oct-26 | 2026-10-01 | Milestone | Medium
Ethiopia | ETH01 | Nov-26 | 2026-11-01 | Milestone | Medium
Ethiopia | ETH01 | Dec-26 | 2026-12-01 | Milestone | Medium
Ethiopia | ETH01 | Jan-27 | 2027-01-01 | Milestone | Medium
Ethiopia | ETH01 | Feb-27 | 2027-02-01 | Milestone | Medium
Ethiopia | ETH02 | Sep-26 | 2026-09-01 | Milestone | Medium
Ethiopia | ETH02 | Oct-26 | 2026-10-01 | Milestone | Medium
Ethiopia | ETH02 | Nov-26 | 2026-11-01 | Milestone | Medium
Ethiopia | ETH02 | Dec-26 | 2026-12-01 | Milestone | Medium
Ethiopia | ETH02 | Jan-27 | 2027-01-01 | Milestone | Medium
Ethiopia | ETH02 | Feb-27 | 2027-02-01 | Milestone | Medium
Ethiopia | ETH03 | Sep-26 | 2026-09-01 | Milestone | Medium
Ethiopia | ETH03 | Oct-26 | 2026-10-01 | Milestone | Medium
Ethiopia | ETH03 | Nov-26 | 2026-11-01 | Milestone | Medium
Ethiopia | ETH03 | Dec-26 | 2026-12-01 | Milestone | Medium
Ethiopia | ETH03 | Jan-27 | 2027-01-01 | Milestone | Medium
Ethiopia | ETH03 | Feb-27 | 2027-02-01 | Milestone | Medium
Ethiopia | ETH04 | Sep-26 | 2026-09-01 | Milestone | Medium
Ethiopia | ETH04 | Oct-26 | 2026-10-01 | Milestone | Medium
Ethiopia | ETH04 | Nov-26 | 2026-11-01 | Milestone | Medium
Ethiopia | ETH04 | Dec-26 | 2026-12-01 | Milestone | Medium
Ethiopia | ETH04 | Jan-27 | 2027-01-01 | Milestone | Medium
Ethiopia | ETH04 | Feb-27 | 2027-02-01 | Milestone | Medium
Ethiopia | ETH05 | Oct-26 | 2026-10-01 | Milestone | Medium
Ethiopia | ETH05 | Nov-26 | 2026-11-01 | Milestone | Medium
Ethiopia | ETH05 | Dec-26 | 2026-12-01 | Milestone | Medium
Ethiopia | ETH05 | Jan-27 | 2027-01-01 | Milestone | Medium
Ethiopia | ETH05 | Feb-27 | 2027-02-01 | Milestone | Medium
Ethiopia | ETH05 | Mar-27 | 2027-03-01 | Milestone | Medium
Ethiopia | ETH06 | Oct-26 | 2026-10-01 | Milestone | Medium
Ethiopia | ETH06 | Nov-26 | 2026-11-01 | Milestone | Medium
Ethiopia | ETH06 | Dec-26 | 2026-12-01 | Milestone | Medium
Ethiopia | ETH06 | Jan-27 | 2027-01-01 | Milestone | Medium
Ethiopia | ETH06 | Feb-27 | 2027-02-01 | Milestone | Medium
Ethiopia | ETH06 | Mar-27 | 2027-03-01 | Milestone | Medium
Ethiopia | ETH07 | Oct-26 | 2026-10-01 | Milestone | Medium
Ethiopia | ETH07 | Nov-26 | 2026-11-01 | Milestone | Medium
Ethiopia | ETH07 | Dec-26 | 2026-12-01 | Milestone | Medium
Ethiopia | ETH07 | Jan-27 | 2027-01-01 | Milestone | Medium
Ethiopia | ETH07 | Feb-27 | 2027-02-01 | Milestone | Medium
Ethiopia | ETH07 | Mar-27 | 2027-03-01 | Milestone | Medium
Ethiopia | ETH07 | Apr-27 | 2027-04-01 | Milestone | Medium
Ethiopia | ETH07 | May-27 | 2027-05-01 | Milestone | Medium
Ethiopia | ETH08 | Nov-26 | 2026-11-01 | Milestone | Medium
Ethiopia | ETH08 | Dec-26 | 2026-12-01 | Milestone | Medium
Ethiopia | ETH08 | Jan-27 | 2027-01-01 | Milestone | Medium
Ethiopia | ETH08 | Feb-27 | 2027-02-01 | Milestone | Medium
Ethiopia | ETH08 | Mar-27 | 2027-03-01 | Milestone | Medium
Ethiopia | ETH08 | Apr-27 | 2027-04-01 | Milestone | Medium
Ethiopia | ETH08 | May-27 | 2027-05-01 | Milestone | Medium
Ethiopia | ETH09 | Nov-26 | 2026-11-01 | Milestone | Medium
Ethiopia | ETH09 | Dec-26 | 2026-12-01 | Milestone | Medium
Ethiopia | ETH09 | Jan-27 | 2027-01-01 | Milestone | Medium
Ethiopia | ETH09 | Feb-27 | 2027-02-01 | Milestone | Medium
Ethiopia | ETH09 | Mar-27 | 2027-03-01 | Milestone | Medium
Ethiopia | ETH09 | Apr-27 | 2027-04-01 | Milestone | Medium
Ethiopia | ETH09 | May-27 | 2027-05-01 | Milestone | Medium
Ethiopia | ETH09 | Jun-27 | 2027-06-01 | Milestone | Medium
Ethiopia | ETH09 | Jul-27 | 2027-07-01 | Milestone | Medium
Ethiopia | ETH09 | Aug-27 | 2027-08-01 | Milestone | Medium
Ethiopia | ETH10 | Sep-26 | 2026-09-01 | Milestone | Medium
Ethiopia | ETH10 | Oct-26 | 2026-10-01 | Milestone | Medium
Ethiopia | ETH10 | Nov-26 | 2026-11-01 | Milestone | Medium
Ethiopia | ETH10 | Dec-26 | 2026-12-01 | Milestone | Medium
Ethiopia | ETH10 | Jan-27 | 2027-01-01 | Milestone | Medium
Ethiopia | ETH10 | Feb-27 | 2027-02-01 | Milestone | Medium
Ethiopia | ETH11 | Dec-26 | 2026-12-01 | Milestone | Medium
Ethiopia | ETH11 | Jan-27 | 2027-01-01 | Milestone | Medium
Ethiopia | ETH11 | Feb-27 | 2027-02-01 | Milestone | Medium
Ethiopia | ETH11 | Mar-27 | 2027-03-01 | Milestone | Medium
Ethiopia | ETH11 | Apr-27 | 2027-04-01 | Milestone | Medium
Ethiopia | ETH11 | May-27 | 2027-05-01 | Milestone | Medium
Ethiopia | ETH11 | Jun-27 | 2027-06-01 | Milestone | Medium
Ethiopia | ETH12 | Dec-26 | 2026-12-01 | Milestone | Medium
Ethiopia | ETH12 | Jan-27 | 2027-01-01 | Milestone | Medium
Ethiopia | ETH12 | Feb-27 | 2027-02-01 | Milestone | Medium
Ethiopia | ETH12 | Mar-27 | 2027-03-01 | Milestone | Medium
Ethiopia | ETH12 | Apr-27 | 2027-04-01 | Milestone | Medium
Ethiopia | ETH12 | May-27 | 2027-05-01 | Milestone | Medium
Ethiopia | ETH12 | Jun-27 | 2027-06-01 | Milestone | Medium
Ethiopia | ETH13 | Dec-26 | 2026-12-01 | Milestone | Medium
Ethiopia | ETH13 | Jan-27 | 2027-01-01 | Milestone | Medium
Ethiopia | ETH13 | Feb-27 | 2027-02-01 | Milestone | Medium
Ethiopia | ETH13 | Mar-27 | 2027-03-01 | Milestone | Medium
Ethiopia | ETH13 | Apr-27 | 2027-04-01 | Milestone | Medium
Ethiopia | ETH13 | May-27 | 2027-05-01 | Milestone | Medium
Ethiopia | ETH13 | Jun-27 | 2027-06-01 | Milestone | Medium
Ethiopia | ETH14 | Jan-27 | 2027-01-01 | Milestone | Medium
Ethiopia | ETH14 | Feb-27 | 2027-02-01 | Milestone | Medium
Ethiopia | ETH14 | Mar-27 | 2027-03-01 | Milestone | Medium
Ethiopia | ETH14 | Apr-27 | 2027-04-01 | Milestone | Medium
Ethiopia | ETH14 | May-27 | 2027-05-01 | Milestone | Medium
Ethiopia | ETH14 | Jun-27 | 2027-06-01 | Milestone | Medium
Ethiopia | ETH14 | Jul-27 | 2027-07-01 | Milestone | Medium
Ethiopia | ETH14 | Aug-27 | 2027-08-01 | Milestone | Medium
Ethiopia | METH0 | Sep-26 | 2026-09-01 | Mobilization (not in budget) | Medium
Ethiopia | METH0 | Oct-26 | 2026-10-01 | Mobilization (not in budget) | Medium
Kenya | KEN01 | Sep-26 | 2026-09-01 | Milestone | High
Kenya | KEN01 | Oct-26 | 2026-10-01 | Milestone | High
Kenya | KEN01 | Nov-26 | 2026-11-01 | Milestone | High
Kenya | KEN01 | Dec-26 | 2026-12-01 | Milestone | High
Kenya | KEN02 | Oct-26 | 2026-10-01 | Milestone | High
Kenya | KEN02 | Nov-26 | 2026-11-01 | Milestone | High
Kenya | KEN02 | Dec-26 | 2026-12-01 | Milestone | High
Kenya | KEN03 | Sep-26 | 2026-09-01 | Milestone | High
Kenya | KEN03 | Oct-26 | 2026-10-01 | Milestone | High
Kenya | KEN03 | Nov-26 | 2026-11-01 | Milestone | High
Kenya | KEN03 | Dec-26 | 2026-12-01 | Milestone | High
Kenya | KEN04 | Sep-26 | 2026-09-01 | Milestone | High
Kenya | KEN04 | Oct-26 | 2026-10-01 | Milestone | High
Kenya | KEN04 | Nov-26 | 2026-11-01 | Milestone | High
Kenya | KEN04 | Dec-26 | 2026-12-01 | Milestone | High
Kenya | KEN05 | Sep-26 | 2026-09-01 | Milestone | High
Kenya | KEN05 | Oct-26 | 2026-10-01 | Milestone | High
Kenya | KEN05 | Nov-26 | 2026-11-01 | Milestone | High
Kenya | KEN05 | Dec-26 | 2026-12-01 | Milestone | High
Kenya | KEN06 | Sep-26 | 2026-09-01 | Milestone | High
Kenya | KEN06 | Oct-26 | 2026-10-01 | Milestone | High
Kenya | KEN06 | Nov-26 | 2026-11-01 | Milestone | High
Kenya | KEN06 | Dec-26 | 2026-12-01 | Milestone | High
Kenya | KEN07 | Sep-26 | 2026-09-01 | Milestone | High
Kenya | KEN07 | Oct-26 | 2026-10-01 | Milestone | High
Kenya | KEN07 | Nov-26 | 2026-11-01 | Milestone | High
Kenya | KEN07 | Dec-26 | 2026-12-01 | Milestone | High
Kenya | MKEN0 | Sep-26 | 2026-09-01 | Mobilization (not in budget) | High
Kenya | MKEN0 | Oct-26 | 2026-10-01 | Mobilization (not in budget) | High
Lesotho | LES01 | Oct-26 | 2026-10-01 | Milestone | High
Lesotho | LES01 | Nov-26 | 2026-11-01 | Milestone | High
Lesotho | LES01 | Dec-26 | 2026-12-01 | Milestone | High
Lesotho | LES01 | Jan-27 | 2027-01-01 | Milestone | High
Lesotho | LES02 | Oct-26 | 2026-10-01 | Milestone | High
Lesotho | LES02 | Nov-26 | 2026-11-01 | Milestone | High
Lesotho | LES02 | Dec-26 | 2026-12-01 | Milestone | High
Lesotho | LES02 | Jan-27 | 2027-01-01 | Milestone | High
Lesotho | LES02 | Feb-27 | 2027-02-01 | Milestone | High
Lesotho | LES02 | Mar-27 | 2027-03-01 | Milestone | High
Lesotho | LES03 | Oct-26 | 2026-10-01 | Milestone | High
Lesotho | LES03 | Nov-26 | 2026-11-01 | Milestone | High
Lesotho | LES03 | Dec-26 | 2026-12-01 | Milestone | High
Lesotho | LES03 | Jan-27 | 2027-01-01 | Milestone | High
Lesotho | LES03 | Feb-27 | 2027-02-01 | Milestone | High
Lesotho | LES03 | Mar-27 | 2027-03-01 | Milestone | High
Lesotho | LES04 | Oct-26 | 2026-10-01 | Milestone | High
Lesotho | LES04 | Nov-26 | 2026-11-01 | Milestone | High
Lesotho | LES04 | Dec-26 | 2026-12-01 | Milestone | High
Lesotho | LES04 | Jan-27 | 2027-01-01 | Milestone | High
Lesotho | LES04 | Feb-27 | 2027-02-01 | Milestone | High
Lesotho | LES04 | Mar-27 | 2027-03-01 | Milestone | High
Lesotho | LES05 | Oct-26 | 2026-10-01 | Milestone | High
Lesotho | LES05 | Nov-26 | 2026-11-01 | Milestone | High
Lesotho | LES05 | Dec-26 | 2026-12-01 | Milestone | High
Lesotho | LES05 | Jan-27 | 2027-01-01 | Milestone | High
Lesotho | LES05 | Feb-27 | 2027-02-01 | Milestone | High
Lesotho | LES05 | Mar-27 | 2027-03-01 | Milestone | High
Lesotho | LES06 | Oct-26 | 2026-10-01 | Milestone | High
Lesotho | LES06 | Nov-26 | 2026-11-01 | Milestone | High
Lesotho | LES06 | Dec-26 | 2026-12-01 | Milestone | High
Lesotho | LES06 | Jan-27 | 2027-01-01 | Milestone | High
Lesotho | LES06 | Feb-27 | 2027-02-01 | Milestone | High
Lesotho | LES06 | Mar-27 | 2027-03-01 | Milestone | High
Lesotho | LES07 | Oct-26 | 2026-10-01 | Milestone | High
Lesotho | LES07 | Nov-26 | 2026-11-01 | Milestone | High
Lesotho | LES07 | Dec-26 | 2026-12-01 | Milestone | High
Lesotho | LES07 | Jan-27 | 2027-01-01 | Milestone | High
Lesotho | LES07 | Feb-27 | 2027-02-01 | Milestone | High
Lesotho | LES07 | Mar-27 | 2027-03-01 | Milestone | High
Lesotho | MLES0 | Oct-26 | 2026-10-01 | Mobilization (not in budget) | High
Madagascar | MAD01 | Oct-26 | 2026-10-01 | Milestone | High
Madagascar | MAD01 | Nov-26 | 2026-11-01 | Milestone | High
Madagascar | MAD01 | Dec-26 | 2026-12-01 | Milestone | High
Madagascar | MAD01 | Jan-27 | 2027-01-01 | Milestone | High
Madagascar | MAD01 | Feb-27 | 2027-02-01 | Milestone | High
Madagascar | MAD02 | Oct-26 | 2026-10-01 | Milestone | High
Madagascar | MAD02 | Nov-26 | 2026-11-01 | Milestone | High
Madagascar | MAD02 | Dec-26 | 2026-12-01 | Milestone | High
Madagascar | MAD02 | Jan-27 | 2027-01-01 | Milestone | High
Madagascar | MAD02 | Feb-27 | 2027-02-01 | Milestone | High
Madagascar | MAD03 | Oct-26 | 2026-10-01 | Milestone | High
Madagascar | MAD03 | Nov-26 | 2026-11-01 | Milestone | High
Madagascar | MAD03 | Dec-26 | 2026-12-01 | Milestone | High
Madagascar | MAD03 | Jan-27 | 2027-01-01 | Milestone | High
Madagascar | MAD03 | Feb-27 | 2027-02-01 | Milestone | High
Madagascar | MAD03 | Mar-27 | 2027-03-01 | Milestone | High
Madagascar | MAD03 | Apr-27 | 2027-04-01 | Milestone | High
Madagascar | MAD04 | Oct-26 | 2026-10-01 | Milestone | High
Madagascar | MAD04 | Nov-26 | 2026-11-01 | Milestone | High
Madagascar | MAD04 | Dec-26 | 2026-12-01 | Milestone | High
Madagascar | MAD04 | Jan-27 | 2027-01-01 | Milestone | High
Madagascar | MAD04 | Feb-27 | 2027-02-01 | Milestone | High
Madagascar | MAD04 | Mar-27 | 2027-03-01 | Milestone | High
Madagascar | MAD04 | Apr-27 | 2027-04-01 | Milestone | High
Madagascar | MAD04 | May-27 | 2027-05-01 | Milestone | High
Madagascar | MAD04 | Jun-27 | 2027-06-01 | Milestone | High
Madagascar | MAD04 | Jul-27 | 2027-07-01 | Milestone | High
Madagascar | MAD04 | Aug-27 | 2027-08-01 | Milestone | High
Madagascar | MAD04 | Sep-27 | 2027-09-01 | Milestone | High
Madagascar | MAD05 | Jan-27 | 2027-01-01 | Milestone | High
Madagascar | MAD05 | Feb-27 | 2027-02-01 | Milestone | High
Madagascar | MAD05 | Mar-27 | 2027-03-01 | Milestone | High
Madagascar | MAD05 | Apr-27 | 2027-04-01 | Milestone | High
Madagascar | MAD05 | May-27 | 2027-05-01 | Milestone | High
Madagascar | MAD05 | Jun-27 | 2027-06-01 | Milestone | High
Madagascar | MAD06 | Oct-26 | 2026-10-01 | Milestone | High
Madagascar | MAD06 | Nov-26 | 2026-11-01 | Milestone | High
Madagascar | MAD06 | Dec-26 | 2026-12-01 | Milestone | High
Madagascar | MAD06 | Jan-27 | 2027-01-01 | Milestone | High
Madagascar | MAD06 | Feb-27 | 2027-02-01 | Milestone | High
Madagascar | MAD06 | Mar-27 | 2027-03-01 | Milestone | High
Madagascar | MAD06 | Apr-27 | 2027-04-01 | Milestone | High
Madagascar | MAD06 | May-27 | 2027-05-01 | Milestone | High
Madagascar | MAD07 | Nov-26 | 2026-11-01 | Milestone | High
Madagascar | MAD07 | Dec-26 | 2026-12-01 | Milestone | High
Madagascar | MAD07 | Jan-27 | 2027-01-01 | Milestone | High
Madagascar | MAD07 | Feb-27 | 2027-02-01 | Milestone | High
Madagascar | MAD07 | Mar-27 | 2027-03-01 | Milestone | High
Madagascar | MAD07 | Apr-27 | 2027-04-01 | Milestone | High
Madagascar | MAD07 | May-27 | 2027-05-01 | Milestone | High
Madagascar | MAD07 | Jun-27 | 2027-06-01 | Milestone | High
Madagascar | MAD08 | Oct-26 | 2026-10-01 | Milestone | High
Madagascar | MAD08 | Nov-26 | 2026-11-01 | Milestone | High
Madagascar | MAD08 | Dec-26 | 2026-12-01 | Milestone | High
Madagascar | MAD08 | Jan-27 | 2027-01-01 | Milestone | High
Madagascar | MAD08 | Feb-27 | 2027-02-01 | Milestone | High
Madagascar | MAD08 | Mar-27 | 2027-03-01 | Milestone | High
Madagascar | MAD08 | Apr-27 | 2027-04-01 | Milestone | High
Madagascar | MAD08 | May-27 | 2027-05-01 | Milestone | High
Madagascar | MAD08 | Jun-27 | 2027-06-01 | Milestone | High
Madagascar | MAD09 | Nov-26 | 2026-11-01 | Milestone | High
Madagascar | MAD09 | Dec-26 | 2026-12-01 | Milestone | High
Madagascar | MAD09 | Jan-27 | 2027-01-01 | Milestone | High
Madagascar | MAD09 | Feb-27 | 2027-02-01 | Milestone | High
Madagascar | MAD09 | Mar-27 | 2027-03-01 | Milestone | High
Madagascar | MAD09 | Apr-27 | 2027-04-01 | Milestone | High
Madagascar | MAD09 | May-27 | 2027-05-01 | Milestone | High
Madagascar | MAD09 | Jun-27 | 2027-06-01 | Milestone | High
Madagascar | MAD10 | Nov-26 | 2026-11-01 | Milestone | High
Madagascar | MAD10 | Dec-26 | 2026-12-01 | Milestone | High
Madagascar | MAD10 | Jan-27 | 2027-01-01 | Milestone | High
Madagascar | MAD10 | Feb-27 | 2027-02-01 | Milestone | High
Madagascar | MAD10 | Mar-27 | 2027-03-01 | Milestone | High
Madagascar | MAD10 | Apr-27 | 2027-04-01 | Milestone | High
Madagascar | MAD10 | May-27 | 2027-05-01 | Milestone | High
Madagascar | MAD10 | Jun-27 | 2027-06-01 | Milestone | High
Madagascar | MAD11 | Dec-26 | 2026-12-01 | Milestone | High
Madagascar | MAD11 | Jan-27 | 2027-01-01 | Milestone | High
Madagascar | MAD11 | Feb-27 | 2027-02-01 | Milestone | High
Madagascar | MAD11 | Mar-27 | 2027-03-01 | Milestone | High
Madagascar | MAD11 | Apr-27 | 2027-04-01 | Milestone | High
Madagascar | MAD11 | May-27 | 2027-05-01 | Milestone | High
Madagascar | MAD11 | Jun-27 | 2027-06-01 | Milestone | High
Madagascar | MAD11 | Jul-27 | 2027-07-01 | Milestone | High
Madagascar | MMAD0 | Oct-26 | 2026-10-01 | Mobilization (not in budget) | High
Madagascar | MMAD0 | Nov-26 | 2026-11-01 | Mobilization (not in budget) | High
Moldova | MMOL0 | Sep-26 | 2026-09-01 | Mobilization (not in budget) | High
Moldova | MMOL0 | Oct-26 | 2026-10-01 | Mobilization (not in budget) | High
Moldova | MMOL0 | Nov-26 | 2026-11-01 | Mobilization (not in budget) | High
Moldova | MMOL0 | Dec-26 | 2026-12-01 | Mobilization (not in budget) | High
Moldova | MOL01 | Sep-26 | 2026-09-01 | Milestone | High
Moldova | MOL01 | Oct-26 | 2026-10-01 | Milestone | High
Moldova | MOL01 | Nov-26 | 2026-11-01 | Milestone | High
Moldova | MOL01 | Dec-26 | 2026-12-01 | Milestone | High
Moldova | MOL01 | Jan-27 | 2027-01-01 | Milestone | High
Moldova | MOL01 | Feb-27 | 2027-02-01 | Milestone | High
Moldova | MOL01 | Mar-27 | 2027-03-01 | Milestone | High
Moldova | MOL01 | Apr-27 | 2027-04-01 | Milestone | High
Moldova | MOL01 | May-27 | 2027-05-01 | Milestone | High
Moldova | MOL02 | Sep-26 | 2026-09-01 | Milestone | High
Moldova | MOL02 | Oct-26 | 2026-10-01 | Milestone | High
Moldova | MOL02 | Nov-26 | 2026-11-01 | Milestone | High
Moldova | MOL02 | Dec-26 | 2026-12-01 | Milestone | High
Moldova | MOL02 | Jan-27 | 2027-01-01 | Milestone | High
Moldova | MOL02 | Feb-27 | 2027-02-01 | Milestone | High
Moldova | MOL02 | Mar-27 | 2027-03-01 | Milestone | High
Moldova | MOL02 | Apr-27 | 2027-04-01 | Milestone | High
Moldova | MOL02 | May-27 | 2027-05-01 | Milestone | High
Moldova | MOL02 | Jun-27 | 2027-06-01 | Milestone | High
Moldova | MOL02 | Jul-27 | 2027-07-01 | Milestone | High
Moldova | MOL02 | Aug-27 | 2027-08-01 | Milestone | High
Moldova | MOL03 | Sep-26 | 2026-09-01 | Milestone | High
Moldova | MOL03 | Oct-26 | 2026-10-01 | Milestone | High
Moldova | MOL03 | Nov-26 | 2026-11-01 | Milestone | High
Moldova | MOL03 | Dec-26 | 2026-12-01 | Milestone | High
Moldova | MOL03 | Jan-27 | 2027-01-01 | Milestone | High
Moldova | MOL03 | Feb-27 | 2027-02-01 | Milestone | High
Moldova | MOL03 | Mar-27 | 2027-03-01 | Milestone | High
Moldova | MOL03 | Apr-27 | 2027-04-01 | Milestone | High
Moldova | MOL03 | May-27 | 2027-05-01 | Milestone | High
Moldova | MOL04 | Sep-26 | 2026-09-01 | Milestone | High
Moldova | MOL04 | Oct-26 | 2026-10-01 | Milestone | High
Moldova | MOL04 | Nov-26 | 2026-11-01 | Milestone | High
Moldova | MOL04 | Dec-26 | 2026-12-01 | Milestone | High
Moldova | MOL04 | Jan-27 | 2027-01-01 | Milestone | High
Moldova | MOL04 | Feb-27 | 2027-02-01 | Milestone | High
Moldova | MOL04 | Mar-27 | 2027-03-01 | Milestone | High
Moldova | MOL04 | Apr-27 | 2027-04-01 | Milestone | High
Moldova | MOL04 | May-27 | 2027-05-01 | Milestone | High
Moldova | MOL04 | Jun-27 | 2027-06-01 | Milestone | High
Moldova | MOL05 | Sep-26 | 2026-09-01 | Milestone | High
Moldova | MOL05 | Oct-26 | 2026-10-01 | Milestone | High
Moldova | MOL05 | Nov-26 | 2026-11-01 | Milestone | High
Moldova | MOL05 | Dec-26 | 2026-12-01 | Milestone | High
Moldova | MOL05 | Jan-27 | 2027-01-01 | Milestone | High
Moldova | MOL05 | Feb-27 | 2027-02-01 | Milestone | High
Moldova | MOL05 | Mar-27 | 2027-03-01 | Milestone | High
Moldova | MOL05 | Apr-27 | 2027-04-01 | Milestone | High
Moldova | MOL05 | May-27 | 2027-05-01 | Milestone | High
Moldova | MOL05 | Jun-27 | 2027-06-01 | Milestone | High
Namibia | MNAM0 | Oct-26 | 2026-10-01 | Mobilization (not in budget) | High
Namibia | NAM01 | Oct-26 | 2026-10-01 | Milestone | High
Namibia | NAM01 | Nov-26 | 2026-11-01 | Milestone | High
Namibia | NAM01 | Dec-26 | 2026-12-01 | Milestone | High
Namibia | NAM02 | Oct-26 | 2026-10-01 | Milestone | High
Namibia | NAM02 | Nov-26 | 2026-11-01 | Milestone | High
Namibia | NAM02 | Dec-26 | 2026-12-01 | Milestone | High
Namibia | NAM03 | Oct-26 | 2026-10-01 | Milestone | High
Namibia | NAM03 | Nov-26 | 2026-11-01 | Milestone | High
Namibia | NAM03 | Dec-26 | 2026-12-01 | Milestone | High
Namibia | NAM03 | Jan-27 | 2027-01-01 | Milestone | High
Namibia | NAM03 | Feb-27 | 2027-02-01 | Milestone | High
Namibia | NAM03 | Mar-27 | 2027-03-01 | Milestone | High
Namibia | NAM04 | Oct-26 | 2026-10-01 | Milestone | High
Namibia | NAM04 | Nov-26 | 2026-11-01 | Milestone | High
Namibia | NAM04 | Dec-26 | 2026-12-01 | Milestone | High
Namibia | NAM04 | Jan-27 | 2027-01-01 | Milestone | High
Namibia | NAM04 | Feb-27 | 2027-02-01 | Milestone | High
Namibia | NAM05 | Oct-26 | 2026-10-01 | Milestone | High
Namibia | NAM05 | Nov-26 | 2026-11-01 | Milestone | High
Namibia | NAM05 | Dec-26 | 2026-12-01 | Milestone | High
Namibia | NAM05 | Jan-27 | 2027-01-01 | Milestone | High
Namibia | NAM05 | Feb-27 | 2027-02-01 | Milestone | High
Namibia | NAM05 | Mar-27 | 2027-03-01 | Milestone | High
Namibia | NAM06 | Oct-26 | 2026-10-01 | Milestone | High
Namibia | NAM06 | Nov-26 | 2026-11-01 | Milestone | High
Namibia | NAM06 | Dec-26 | 2026-12-01 | Milestone | High
Namibia | NAM06 | Jan-27 | 2027-01-01 | Milestone | High
Namibia | NAM06 | Feb-27 | 2027-02-01 | Milestone | High
Namibia | NAM06 | Mar-27 | 2027-03-01 | Milestone | High
Namibia | NAM07 | Jan-27 | 2027-01-01 | Milestone | High
Namibia | NAM07 | Feb-27 | 2027-02-01 | Milestone | High
Namibia | NAM07 | Mar-27 | 2027-03-01 | Milestone | High
Namibia | NAM08 | Oct-26 | 2026-10-01 | Milestone | Medium
Namibia | NAM08 | Nov-26 | 2026-11-01 | Milestone | Medium
Namibia | NAM08 | Dec-26 | 2026-12-01 | Milestone | Medium
Namibia | NAM08 | Jan-27 | 2027-01-01 | Milestone | Medium
Namibia | NAM08 | Feb-27 | 2027-02-01 | Milestone | Medium
Namibia | NAM08 | Mar-27 | 2027-03-01 | Milestone | Medium
Namibia | NAM09 | Oct-26 | 2026-10-01 | Milestone | High
Namibia | NAM09 | Nov-26 | 2026-11-01 | Milestone | High
Namibia | NAM09 | Dec-26 | 2026-12-01 | Milestone | High
Namibia | NAM09 | Jan-27 | 2027-01-01 | Milestone | High
Namibia | NAM09 | Feb-27 | 2027-02-01 | Milestone | High
Namibia | NAM09 | Mar-27 | 2027-03-01 | Milestone | High
Namibia | NAM10 | Oct-26 | 2026-10-01 | Milestone | High
Namibia | NAM10 | Nov-26 | 2026-11-01 | Milestone | High
Namibia | NAM10 | Dec-26 | 2026-12-01 | Milestone | High
Namibia | NAM10 | Jan-27 | 2027-01-01 | Milestone | High
Namibia | NAM10 | Feb-27 | 2027-02-01 | Milestone | High
Namibia | NAM10 | Mar-27 | 2027-03-01 | Milestone | High
Niger | MNIG0 | Oct-26 | 2026-10-01 | Mobilization (not in budget) | High
Niger | NIG01 | Oct-26 | 2026-10-01 | Milestone | High
Niger | NIG01 | Nov-26 | 2026-11-01 | Milestone | High
Niger | NIG01 | Dec-26 | 2026-12-01 | Milestone | High
Niger | NIG01 | Jan-27 | 2027-01-01 | Milestone | High
Niger | NIG01 | Feb-27 | 2027-02-01 | Milestone | High
Niger | NIG02 | Oct-26 | 2026-10-01 | Milestone | High
Niger | NIG02 | Nov-26 | 2026-11-01 | Milestone | High
Niger | NIG02 | Dec-26 | 2026-12-01 | Milestone | High
Niger | NIG02 | Jan-27 | 2027-01-01 | Milestone | High
Niger | NIG02 | Feb-27 | 2027-02-01 | Milestone | High
Niger | NIG03 | Oct-26 | 2026-10-01 | Milestone | High
Niger | NIG03 | Nov-26 | 2026-11-01 | Milestone | High
Niger | NIG03 | Dec-26 | 2026-12-01 | Milestone | High
Niger | NIG03 | Jan-27 | 2027-01-01 | Milestone | High
Niger | NIG03 | Feb-27 | 2027-02-01 | Milestone | High
Niger | NIG03 | Mar-27 | 2027-03-01 | Milestone | High
Niger | NIG03 | Apr-27 | 2027-04-01 | Milestone | High
Niger | NIG04 | Oct-26 | 2026-10-01 | Milestone | High
Niger | NIG04 | Nov-26 | 2026-11-01 | Milestone | High
Niger | NIG04 | Dec-26 | 2026-12-01 | Milestone | High
Niger | NIG04 | Jan-27 | 2027-01-01 | Milestone | High
Niger | NIG04 | Feb-27 | 2027-02-01 | Milestone | High
Niger | NIG04 | Mar-27 | 2027-03-01 | Milestone | High
Niger | NIG04 | Apr-27 | 2027-04-01 | Milestone | High
Niger | NIG05 | Oct-26 | 2026-10-01 | Milestone | High
Niger | NIG05 | Nov-26 | 2026-11-01 | Milestone | High
Niger | NIG05 | Dec-26 | 2026-12-01 | Milestone | High
Niger | NIG05 | Jan-27 | 2027-01-01 | Milestone | High
Niger | NIG05 | Feb-27 | 2027-02-01 | Milestone | High
Niger | NIG05 | Mar-27 | 2027-03-01 | Milestone | High
Niger | NIG05 | Apr-27 | 2027-04-01 | Milestone | High
Niger | NIG05 | May-27 | 2027-05-01 | Milestone | High
Niger | NIG06 | Oct-26 | 2026-10-01 | Milestone | High
Niger | NIG06 | Nov-26 | 2026-11-01 | Milestone | High
Niger | NIG06 | Dec-26 | 2026-12-01 | Milestone | High
Niger | NIG06 | Jan-27 | 2027-01-01 | Milestone | High
Niger | NIG06 | Feb-27 | 2027-02-01 | Milestone | High
Niger | NIG06 | Mar-27 | 2027-03-01 | Milestone | High
Niger | NIG06 | Apr-27 | 2027-04-01 | Milestone | High
Niger | NIG06 | May-27 | 2027-05-01 | Milestone | High
Niger | NIG07 | Oct-26 | 2026-10-01 | Milestone | High
Niger | NIG07 | Nov-26 | 2026-11-01 | Milestone | High
Niger | NIG07 | Dec-26 | 2026-12-01 | Milestone | High
Niger | NIG07 | Jan-27 | 2027-01-01 | Milestone | High
Niger | NIG07 | Feb-27 | 2027-02-01 | Milestone | High
Niger | NIG07 | Mar-27 | 2027-03-01 | Milestone | High
Niger | NIG07 | Apr-27 | 2027-04-01 | Milestone | High
Niger | NIG07 | May-27 | 2027-05-01 | Milestone | High
Niger | NIG07 | Jun-27 | 2027-06-01 | Milestone | High
Niger | NIG07 | Jul-27 | 2027-07-01 | Milestone | High
Niger | NIG08 | Nov-26 | 2026-11-01 | Milestone | High
Niger | NIG08 | Dec-26 | 2026-12-01 | Milestone | High
Niger | NIG08 | Jan-27 | 2027-01-01 | Milestone | High
Niger | NIG08 | Feb-27 | 2027-02-01 | Milestone | High
Niger | NIG08 | Mar-27 | 2027-03-01 | Milestone | High
Niger | NIG08 | Apr-27 | 2027-04-01 | Milestone | High
Niger | NIG08 | May-27 | 2027-05-01 | Milestone | High
Niger | NIG08 | Jun-27 | 2027-06-01 | Milestone | High
Niger | NIG08 | Jul-27 | 2027-07-01 | Milestone | High
Niger | NIG09 | Oct-26 | 2026-10-01 | Milestone | High
Niger | NIG09 | Nov-26 | 2026-11-01 | Milestone | High
Niger | NIG09 | Dec-26 | 2026-12-01 | Milestone | High
Niger | NIG09 | Jan-27 | 2027-01-01 | Milestone | High
Niger | NIG09 | Feb-27 | 2027-02-01 | Milestone | High
Niger | NIG09 | Mar-27 | 2027-03-01 | Milestone | High
Niger | NIG09 | Apr-27 | 2027-04-01 | Milestone | High
Niger | NIG09 | May-27 | 2027-05-01 | Milestone | High
Niger | NIG09 | Jun-27 | 2027-06-01 | Milestone | High
Niger | NIG09 | Jul-27 | 2027-07-01 | Milestone | High
Niger | NIG10 | Oct-26 | 2026-10-01 | Milestone | High
Niger | NIG10 | Nov-26 | 2026-11-01 | Milestone | High
Niger | NIG10 | Dec-26 | 2026-12-01 | Milestone | High
Niger | NIG10 | Jan-27 | 2027-01-01 | Milestone | High
Niger | NIG10 | Feb-27 | 2027-02-01 | Milestone | High
Niger | NIG10 | Mar-27 | 2027-03-01 | Milestone | High
Niger | NIG10 | Apr-27 | 2027-04-01 | Milestone | High
Niger | NIG10 | May-27 | 2027-05-01 | Milestone | High
Niger | NIG10 | Jun-27 | 2027-06-01 | Milestone | High
Niger | NIG10 | Jul-27 | 2027-07-01 | Milestone | High
Niger | NIG10 | Aug-27 | 2027-08-01 | Milestone | High
Nigeria | MNRA0 | Oct-26 | 2026-10-01 | Mobilization (not in budget) | High
Nigeria | MNRA0 | Nov-26 | 2026-11-01 | Mobilization (not in budget) | High
Nigeria | MNRA0 | Dec-26 | 2026-12-01 | Mobilization (not in budget) | High
Nigeria | NRA01 | Oct-26 | 2026-10-01 | Milestone | High
Nigeria | NRA01 | Nov-26 | 2026-11-01 | Milestone | High
Nigeria | NRA01 | Dec-26 | 2026-12-01 | Milestone | High
Nigeria | NRA02 | Oct-26 | 2026-10-01 | Milestone | High
Nigeria | NRA02 | Nov-26 | 2026-11-01 | Milestone | High
Nigeria | NRA02 | Dec-26 | 2026-12-01 | Milestone | High
Nigeria | NRA03 | Oct-26 | 2026-10-01 | Milestone | High
Nigeria | NRA03 | Nov-26 | 2026-11-01 | Milestone | High
Nigeria | NRA03 | Dec-26 | 2026-12-01 | Milestone | High
Nigeria | NRA04 | Oct-26 | 2026-10-01 | Milestone | High
Nigeria | NRA04 | Nov-26 | 2026-11-01 | Milestone | High
Nigeria | NRA04 | Dec-26 | 2026-12-01 | Milestone | High
Nigeria | NRA05 | Oct-26 | 2026-10-01 | Milestone | High
Nigeria | NRA05 | Nov-26 | 2026-11-01 | Milestone | High
Nigeria | NRA05 | Dec-26 | 2026-12-01 | Milestone | High
Nigeria | NRA06 | Oct-26 | 2026-10-01 | Milestone | High
Nigeria | NRA06 | Nov-26 | 2026-11-01 | Milestone | High
Nigeria | NRA06 | Dec-26 | 2026-12-01 | Milestone | High
Nigeria | NRA07 | Oct-26 | 2026-10-01 | Milestone | High
Nigeria | NRA07 | Nov-26 | 2026-11-01 | Milestone | High
Nigeria | NRA07 | Dec-26 | 2026-12-01 | Milestone | High
Nigeria | NRA08 | Oct-26 | 2026-10-01 | Milestone | High
Nigeria | NRA08 | Nov-26 | 2026-11-01 | Milestone | High
Nigeria | NRA08 | Dec-26 | 2026-12-01 | Milestone | High
Nigeria | NRA09 | Oct-26 | 2026-10-01 | Milestone | High
Nigeria | NRA09 | Nov-26 | 2026-11-01 | Milestone | High
Nigeria | NRA09 | Dec-26 | 2026-12-01 | Milestone | High
Nigeria | NRA10 | Oct-26 | 2026-10-01 | Milestone | High
Nigeria | NRA10 | Nov-26 | 2026-11-01 | Milestone | High
Nigeria | NRA10 | Dec-26 | 2026-12-01 | Milestone | High
Nigeria | NRA11 | Oct-26 | 2026-10-01 | Milestone | High
Nigeria | NRA11 | Nov-26 | 2026-11-01 | Milestone | High
Nigeria | NRA11 | Dec-26 | 2026-12-01 | Milestone | High
Nigeria | NRA12 | Oct-26 | 2026-10-01 | Milestone | High
Nigeria | NRA12 | Nov-26 | 2026-11-01 | Milestone | High
Nigeria | NRA12 | Dec-26 | 2026-12-01 | Milestone | High

## Discrepancies
Country / Budget | Milestone | Check | What disagrees / what I did
Namibia | NAM08 | Gantt vs. Planned End / Workplan tab | Gantt bar ends Feb-27, but Planned End on the timeline tab and the Workplan tab both say Mar-27; recommended window follows the two text sources.
CORE G2G | T1.5 | Word doc cross-check | Header 'Start/End' and Planned Milestone Date say Aug-2027, and the Gantt title says 'FY2027 (Sep 2026 to Aug 2027)', but 5 activities (A1, A12-A15) and the Gantt run to Sep-2027. Followed activity-level evidence; if Aug-27 is right, drop Sep-27.
CORE-HIC | C1a | Word doc cross-check | GANTT DISAGREES: the C1a bars are compressed into Sep-Dec 2026 (e.g. A12 publication shown Dec-26 vs Mar-27 in the table; A4-A11 start/end 1-2 months early), plus a Jan-Aug 2027 'kit maintenance' row (A13) that has no activity-table row (the text assigns maintenance to C1b). Followed the activity table. Header start is Oct-26; A1-A3 begin Sep-26.
CORE-HIC | C1b | Word doc cross-check | Header says Month 1 (Oct-26)..Month 11 (Aug-27) while the progress-review table lists 'Final Achievement' at Month 12 (Sep-27); A1 starts Sep-26. Gantt row A11 has a Jul-27 gap (Jun and Aug only) vs. table Jun-Aug. Table lists activity 'C1b-A17' (likely A7).
CORE-EMR ECHIS | C2 | Word doc cross-check | Doc never states what calendar month 'Month 1' is. Month 1 = Oct-26 is inferred: Q3 reviews at M7-M9 (Apr-Jun) and the T1.8/C2 planned milestone date of 14 Sep 2027 only fit Oct-26 start.
CORE-EMR ECHIS | T1.8 | Word doc cross-check | Same Month 1 = Oct-26 inference as C2. Minor: T1.8-A05 table says M1-M2, Gantt shows M2 only.
CORE-Ebola | E1 | Word doc cross-check | CONFLICT: milestone header End Month and Planned Milestone Date say Sep-2027 (Q4 FY2027), and the summary Gantt shades Jan-Sep, but every activity ends by Jun-27 and all E1 evidence is due Q3 FY2027. Window shown = activity window; extend to Sep-27 if the header governs.
CORE-Ebola | E2 | Word doc cross-check | CONFLICT: milestone header Start Month says October 2026, but the first activity (E2-A1.1) starts Jan-27 in the table and both Gantts. Followed the activities.
CORE-Ebola | E3 | Word doc cross-check | SUMMARY GANTT DISAGREES: it shades E3 Jan-Sep 2027 like the other EVD milestones; the header, the activity table (E3-A1 starts M1) and the detailed Gantt all start Oct-26.

## Coverage
Budget | Status | Detail
Honduras | NO WORKPLAN PROVIDED | Budget has HON01-HON04; no workplan file in the upload.
Sierra Leone | NO WORKPLAN PROVIDED | Budget has SIL01-SIL03; no workplan file in the upload. (The HIC doc lists Sierra Leone only as a C1b implementation country.)
DRC | Partial source | No DRC country workplan file; DRC00-DRC09 months come only from the 'DRC AFGHS-P Foundation' rows of the DRC/EVD Word doc's Gantts.
All other budgets | Covered | Every budget milestone column has a valid-months row (mobilization rows are extra, with no budget column).